ONDO STATE HEALTH SECTOR

2017-2019

Medium Term Sector Strategy (MTSS)

October, 2016

# Foreword

The Medium Term Sector Strategy (MTSS), a complementary component of the Medium-Term Expenditure Framework (MTEF), represents a vital link in the process of translating the long and medium-term health reform strategies of the Ondo State Government from 2017 to 2019 into the spending reality of the Annual Budgets. The Medium Term Sector Strategy of the Health Sector as presented in this document sets out the fully costed initiatives and expenditure plans through which the Sector seeks to contribute to the delivery of qualitative and accessible health care service delivery of government over the period 2017-2019 within the confines of limited scarce resources.

The Medium Term Sector Strategy of the Health Sector was developed by the MTSS Steering Committee and the Sector Planning Team (SPT); comprising, the Honourable Commissioner, the Permanent Secretary, Directors from the Ministry, Departments and Agencies, all key officers from the main Ministry and the Departments and Agencies; with the assistance of the Ministry of Economic Planning and Budget (MEPB) which acted as the coordinating Ministry over the MTSS process.

I wish to commend all stakeholders within the Health sector who tirelessly contributed to the development of the MTSS Document which will serve as an important instrument for guiding policy direction and delivering value for money, in addition to contributing adequately to the socio economic status, improved health care service delivery and expected health outcomes in Ondo State and Nigeria as a whole.

Dr. E.T. Oni

Permanent Secretary (MOH)

October, 2016

# Acknowledgements

- The immense contribution(s) of the Ministry of Economic Planning & Budget for the sense of direction towards achieving and accomplishing this document is hereby acknowledged. Also worthy of note are the contributions of  the World Bank and the following stakeholders to the success of this document:

- Honourable Commissioner for Health,

- Permanent Secretary of the Ministry of Health,

- Secretary of Hospitals Management Board

- Executive Secretary of Ondo State Primary Health Care Development Board (OSPHCDB),

- Directors and Staff of all MDAs in the Health Sector,

- The Principals of the Schools of Nursing, Midwifery and Health Technology,

- The State House of Assembly for enacting relevant laws and approval of the State’s annual budget; Central planning MDAs –SMEPB and SMOF – for providing guidance on the MTSS and resource envelopes available to each sector;

- Sector line ministries and other MDAs for developing the suite of programmes/activities to be implemented by the sector through the MTSS period and for drafting the MTSS document;

- Civil Society and the general public for providing feedback on the current levels of service provision this establishes the gaps in service provision and informs the formulation of new strategies; and

- The Health Sector MTSS Planning Team.

# Contents

Foreword	ii

Acknowledgements	ii

Contents	ii

Table of Figures	ii

List of Tables	ii

Table of Acronyms	ii

Executive Summary	ii

Chapter 1.	Introduction	2

1.1. Aims and objectives of the document	2

1.2. Summary of the process used	2

1.3. Outline of the Structure of the Document	2

Chapter 2.	The Sector and Policy in the State	2

2.1	A brief background to the State	2

2.1.1. Ondo State	2

2.1.2. Geography	2

2.1.3. Economy	2

2.2	A brief introduction to the Sector	2

2.3	The current situation in the Sector	2

2.4	Overview of the sector’s institutional structure	2

2.5	Statement of the sector’s mission, vision and core values	2

2.6	Sector Policy	2

2.7	The sector’s goals and programmes for the MTSS period	2

Chapter 3.	The Development of Sector Strategy	2

3.1	Major Strategic Challenges	2

3.2	Resource Constraints	2

3.3	Contributions from partners	2

3.4	Program connections between Sector MDAs	2

3.5	Outline of Key Strategies	2

3.6	Justification	2

3.7	Result Framework	2

3.8	Responsibilities and Operational Plan	2

Chapter 4.	Three Year Expenditure Projections	2

4.1	Performance Monitoring and Evaluation	2

4.2	Public Involvement	2

5.1	Identifying Sources of Data against the Results Framework	2

5.2	Conducting Annual Sector Review	2

5.3	Organisational Arrangements	2

# Table of Figures

Figure 1: Organogram of the Health Sector	2

# List of Tables

Table 1: Operational Definition of Sector's Core Values	2

Table 2: Summary of 2015 Budget Data for the Sector	2

Table 3: Summary of 2016 Budget Data for the Sector (Jan-April/May 2016)	2

Table 4: Capital Costs Commitments	2

Table 5: Personnel Costs – Existing and Projected	2

Table 6: Overhead Costs – Existing and Projected	2

Table 7: Summary of Cancelled/Shut Down Projects	2

Table 8: Grants and Donor Funding	2

Table 9: Summary of Projects’ Expenditures and Output Measures	2

Table 10: Data Sources for Outcome and Output KPIs	2

# Table of Acronyms

| Acronym | Definition |
| --- | --- |
| AIDS | Acquired Immune Deficiency Syndrome |
| CEMDOS | Confidential Enquiry into Maternal Deaths in Ondo State |
| CSO | Civil Society Organizations |
| DHIS | District Health Information Software |
| DLI | Disbursement Linked Indicator |
| DST | Dental Student Technician |
| EMS | Emergency Medical Services |
| FAST | First Aid Support Team |
| GH | General Hospital |
| HDC | Health Development Committee |
| HIV | Human Immuno-deficiency Virus |
| HMB | Hospitals’ Management Board |
| HMIS | Health Management Information Systems |
| HR | Human Resource |
| HRH | Human Resources for Health |
| ICT | Information and Communication Technology |
| IEC | Information and Education Communication |
| IGR | Internally Generated Revenue |
| KCC | Kidney Care Centre |
| LACA | Local Action Committee on AIDS |
| LGA | Local Government Area |
| LM | Line Ministries |
| LMCU | Logistics Management and Coordinating Unit |
| MCH | Mother and Child Hospital |
| MDA | Ministry Department and Agency |
| MDCN | Medical and Dental Council of Nigeria |
| MEC | Millennium Eye Centre |
| MEPB | Ministry of Economic Planning and Budget |
| MICS | Multiple Indicator Cluster Survey |
| MTSS | Medium Term Sector Strategy |
| MoH | Ministry of Health |
| N&MCN | Nursing and Midwifery Council of Nigeria |
| NDHS | Nigeria Demographic and Health Survey |
| NHIS | National Health Insurance Scheme |
| NHMIS | National Health Management Information Systems |
| NISONMG | Nigerian Schools of Nursing and Midwifery Games |
| NPHCDA | National Primary Health Care Development Agency |
| ODSACA | Ondo State Agency for the Control of AIDS |
| ORIREWA | Ondo Routine Immunization Reaching Every Ward Always |
| OSPHCDB | Ondo State Primary Health Care Development Board |
| PHC | Primary Health Care |
| PMR | Performance Management Review |
| PMTCT | Prevention of Mother to Child Transmission |
| SACA | State Agency for the Control of AIDS |
| SMoH | State Ministry of Health |
| SON | School of Nursing |
| SPT | Sector Planning Team |
| SSH | State Specialist Hospital |
| SSHDP | State Strategic Health Development Plan |
| SURE-P | Subsidy Reinvestment Programme |
| SOM | School of Midwifery |
| TBAs | Traditional Birth Attendants |
| TBL | Tuberculosis and Leprosy |

# Executive Summary

The Ondo State Government is currently preparing the 2017-2019 MTSS document. This is to plan and improve the performance of the Health Sector.

The Year 2015 Budget analysis showed that out of N12,713,642,518.69 allocated to the health sector, N1,976,000,345.37 was expended, meaning a performance of 17.2%. Additionally in the Year 2016 so far from the calendar year between Jan-May, there has been a budget release of 3,708,576,301.23 out of the budget allocation of 13,900,236,540.11. This gives a budget performance of 26.68% midyear (May) which is bound to increase as the year progresses.

Further review of the budget revealed that the MDAs would have performed better but due to the economic recession the country is experiencing.

The preparation of the Health Sector 2017-2019 MTSS will set the pace for the 2017 budget and subsequent ones, as the 2016 budget for the State has been passed and approved. The budget for the year 2016 of Ondo State is N123,720,700,000.00 with a budget allocation of N14,305,790,540.27 (11.56% of the total budget) to the Health sector.

- Introduction

  - Aims and objectives of the document

The Medium Term Sector Strategy (MTSS) takes a prominent role as one of the major milestones in the cyclical chain of the Medium Term Framework.  The MTSS document for the Health Sector is therefore developed to facilitate better harmonization of government policies and strategies with the budgetary process. It is believed that this document when finalized will help inform the development of feasible health programs and projects.

The MTSS is aimed at ensuring that within the given resource envelope, sector resources are deployed in consonance with clearly defined and accountable policy objectives of government of Ondo State.

The process seeks to ensure the achievement of sector targets through feasible and responsive plans where resources are efficiently and effectively deployed.

  - Summary of the process used

The MTSS of the Health Sector as set out in this document was formulated by the Sector Planning Team (SPT); comprising, the Honourable Commissioner, the Permanent Secretary, Directors from the Ministry, Departments and Agencies (MDAs), with the assistance of the Ministry of Economic Planning and Budget (MEPB) which acted as the coordinating Ministry over the MTSS process.

The formulation of the MTSS for the Health Sector was designed to rely on the inputs and support from a range of relevant stakeholders within and outside government who participated actively in the process to ensure that the expenditure plans take effect. These stakeholders include:

- Honourable Commissioner

- Permanent Secretary

- Heads of Departments and Agencies

- Sector Planning Team

- Civil Society Organizations (CSOs) and

- The key planning, budgeting and reform MDA of the Ondo State Government

The process involved the following steps:

- Review of all existing high level policies of government as it relates to the Health sector in line with the government’s strategies of ensuring improved health outcome.

- Confirmation of the Sector’s Goals and Programmes for 2017 – 2019 against the background of government’s strategies.

- Assessment of the existing budget commitments to the Health sector so as to determine the level at which these will accomplish the Goals and Programmes and existing resource commitment reality of the sector

- Development of proposals of projects, existing and new, required to achieve the Goals and Programmes of the sector as defined or validated.

- Use of the Scoring matrix to score projects. This is a veritable tool for planning programmes and projects that are existing and ongoing and completed.

- Prioritization of initiatives and development of detailed costing of each project.

- Identification of the phases of the cost of the prioritized projects over the period 2017 – 2019 and justification of projects based on their high priorities and importance

- Specification of Outputs, Outcomes, Performance Measures and Key Performance Indicators for each project identified in line with the envelope – i.e., the benefits of the projects to the good people of Ondo State.

- Finally, the Log frames of the projects present the goals and programmes of the MDAs in the health sector of Ondo State.

Ondo State high-level policy documents that deal with the Health sector were also reviewed; namely

- Ondo State Government State Strategic Health Development Plan

- Ondo State Caring Heart Agenda

- Ondo State Economic Empowerment and Development Strategy

- Ondo State Vision 20:2020

- Ondo State Operational Plan

The foregoing policy documents were reappraised to obtain relevant strategic issues, policy thrust, high-level strategies, performance measures and targets that form the basis of the health sector MTSS for the period 2017– 2019. Specifically, the review of the policy documents guided the development of the strategic goals, programmes, projects, performance measures, outputs, targets, and outcomes for the 2017– 2019 MTSS of the Health Sector. Highlights of the review are harmonized in the Ondo State Development Plan.

  - Outline of the Structure of the Document

The document was prepared sequentially thus:

Chapter one states the aims and objectives of the document as well as the procedures used in developing the MTSS for Health sector.

Chapter Two gives a brief background of Ondo State as well as discusses the Health Sector in the State by highlighting the institutional structure, current situation, the sector’s vision, mission and core values. The sector policies, goals and programmes for MTSS were also discussed.

Chapter Three states major strategic direction of the sector, resource constraint, contributions from partners, programme connection between sector’s MDAs, outline of key strategies, justification, result framework as well as responsibilities and operational plan.

Chapter Four discusses performance monitoring and evaluation as well as public involvement.

Chapter Five presents sources of data as against the result framework, annual sector review and organizational arrangement.

- The Sector and Policy in the State

  - A brief background to the State

### Ondo State

Ondo State, generally referred to as the “Sunshine State”, was created from the defunct Western State on 3rd February, 1976.  Before its creation, the State existed as the Ondo Province of the old Western State.  The present Ondo State was formed when Ekiti State was carved out of it in October 1996. The State has land area of approximately 15,317sq kilometers representing 1.66 percent of the total surface area of Nigeria. The population of the State in the 1991 census figures was 2,249,548 while year 2006 census puts the population at 3,441,024 made up of 1,745,058 males and 1,715,820 females representing 50.42% and 49.58%, respectively. Ondo State has the longest coastline in Nigeria with considerable territorial waters offshore, rich in aquatic and mineral resources of significant quantity.

### Geography

Ondo State is located within Latitude 50 45’ and 70 52’N and Longitudes 4020’ and 6005’ E.  The Administrative capital is Akure while there are 18 local governments in the State and is bounded in the North by Ekiti and Kogi States, in the East by Edo State, on the West by Osun and Ogun States and in the South by the Atlantic Ocean. Ondo State is located entirely within the tropics.

The tropical climate of the State is broadly of two seasons:  rainy season (April-October) and dry season (November – March).  The temperature throughout the year ranges between 21oC to 29oC and humidity is relatively high.  The annual rainfall varies from 2,000mm in the southern areas to 1,150mm in the northern areas.  The State enjoys luxuriant vegetation with high forest zone (rain forest) in the south and sub-savannah forest in the northern fringe.

The geology of the State is made up of the basement complex. The basement complex is essentially non-porous and water can only be found in the crevices of the complex. The rock types include quartz, gneisses and schists. This basement complex primarily underlies the sedimentary layers which consist of cretaceous, tertiary and quaternary sediments deposited in the coastal basin.

### Economy

The State’s Economy is basically agrarian with large scale production of cocoa, palm produce and rubber. Other crops like maize, Kolanut, yam and cassava are produced in large quantities. 65% percent of the State’s labour force is in the agriculture sub-sector.

The State is also blessed with very rich forest resources where some of the most exotic timber in Nigeria abound.

Ondo State is equally blessed with extensive deposits of crude oil, bitumen, glass sand, kaolin, granites and limestone. Therefore, the State has great potentials for rapid industrial growth in view of its raw materials base.  The tourism potentials of the State is also high as its historical sites, long coastline, lakes, forest and cultural events can be developed for tourism. The fact that Ondo State is arguably the most Peaceful State in the Oil Rich Niger-Delta region, made her the most viable investment destination of all times.

  - A brief introduction to the Sector

The Health sector came into being in April 1976 as a consequence of the creation of Ondo State in February of the same year from the defunct Western State of Nigeria. Within the framework of the defunct Western State Health Management Board System, which came into force by Edict 12 of 1975 on 1st July of the same year, the newly created geo political block inherited the Akure Health Zones.

At inception, the Ministry of Health was divided into 8 divisions namely:

- Administration & General,

- Finance & Establishment

- Curative

- Preventive

- Dental

- Pharmacy

- Nursing

- Training institutions.

The population of human resource in the sector is as follows:

Ministry of health								 324

Hospitals’ Management Board						 4,087

Ondo State Primary Health Care Development Board			 384

Primary Health Care (PHC) workers under Local government payroll 	4,900

Source: Department of Planning Research and Statistics MoH, HMB, OSPHCDB October 2016

  - The current situation in the Sector

The Ministry of Health is the Supervising Ministry for the Health sector of Ondo State and headed by the Honorable Commissioner for Health. It is one of the cardinal ministries of the Ondo State government and besides its oversight function, it has the responsibility of providing policy direction and at the same time supervising its implementation for overall health system development in the state. Its services are provided by broad spectrum of health care institutions both public and private.  These institutions offer either technical and or specialized services while some provide training/production of health care personnel.   The Hospitals Management Board(HMB) is responsible for the management of all personnel of secondary  and tertiary health facilities which include all General Hospitals, Specialist Hospitals, Mother & Child Hospitals, Trauma & Surgical Centre, Kidney Care Centre; The Ondo State Primary Health Care Development Board is responsible for management of all personnel in the primary health care domain of the health system and implement primary healthcare programs & interventions; The Emergency Medical Services  provide emergency rescue and evacuation of accident victim from across the boundaries of the State to the nearest health facility were help and hope can be secured for the victims; The School of Nursing, School of Midwifery and School of Health Technology are also quasi autonomous institution of learning were skilled health workers are produced.  The University of Medical Science, a mono university, is the latest development in the state and would be responsible for producing highly skilled medical workers. The tables and figures below shows improvement in the health sector in terms of increase in facility utilization, improved service delivery  efficiency in local government, reduction in maternal mortality.

Trend of key indicators in the health sector:

Table 1: Health Indices of Ondo State

| POPULATION (2006 Census) | ONDO |  |
| --- | --- | --- |
| Total population | 3,460,877 | 4,301,750 |
| female | 1,715,820 |  |
| male | 1,745,057 |  |
| Under 5 years (20% of Total Pop) | 439,479 |  |
| Adolescents (10 – 24 years) | 1,151,477 |  |
| INDICATORS | NDHS 2008 | NDHS 2013 |
| Literacy rate (female) | 75% |  |
| Literacy rate (male) | 80% |  |
| Total Fertility Rate | 4.9 | 5.2 |
| Use of FP modern method by married women 15-49 | 15% | 31.10% |
| Ante Natal Care provided by skilled Health worker | 70% | 78.60% |
| Skilled attendants at birth | 51% | 67.20% |
| Delivery in Health Facility | 47% | 56.20% |
| Children 12-23 months with full immunization coverage | 37% | 47.20% |
| Wasting in Under 5 children | 6% | 13.40% |
| Diarrhea in children | 6.6 |  |
| ITN ownership | 5% | 36.60% |
| ITN utilization (children) | 4% | 35.50% |
| ITN utilization (pregnant women) | 1% | 41.50% |
| children under 5 with fever receving malaria treatment | - | 38.50% |
| Pregnant women receving IPT | 5% | 10.70% |
| Comprehensive knowledge of HIV (female) | 20% | 9.80% |
| Comprehensive knowledge of HIV (male) | 33% | 16.40% |

Source: DHIS 2.0 report for Ondo State

Figure 1: Total Health Facility Attendance in the State

Figure 2: Trend of some key indicators of maternal & child health for years 2013 & 2014

Source: DHIS 2.0 report for Ondo State

Figure 3: 2014 performance of LGAs using service output against population per 100,000

Source: DHIS 2.0 report for Ondo State

Figure 4: Maternal death profile of the State

Source: CEMDOS, 2015

Sources of fund

|  | 2003 | 2004 | 2005 |
| --- | --- | --- | --- |
| Provider Of services Provider Of services |  |  |  |
| Expenditure Items |  |  |  |
|  | Source: National Health Account 2003-2005 |  |  |
|  | NB: NHA 2006-2009(not disaggregated |  |  |

Figure 5: Trend in Ondo State Total Health expenditure

Despite the improvement in healthcare service delivery in Ondo State, it is also faced with some challenges which are enumerated below:

- Inadequate Budgetary allocation for Health, which is below the 15% Abuja Declaration by the African heads of government in April, 2001.

- Difficult terrains/hard to reach communities constitute almost 33% of total settlements in the state,

- Inadequate human resource for health

- Unpredictable alternative funding source for health

- Extensive Government involvement in market pricing for health

  - Overview of the sector’s institutional structure

The Health sector is one of the cardinal and pivotal sectors of the state government and has the responsibility of providing policy direction for the health system development. It is an essential area of social service delivery to the populace. The sector comprises the Ministry of Health, 4 Agencies and 3 training schools.

(a) The Ministry comprises of the following departments:

- Planning Research & Statistics,

- Hospital Services,

- Public Health,

- Nursing Services,

- Pharmaceutical services, and

- Finance & Administration and Accounts.

(b) The agencies that are responsible for the execution of specific elements of the sector's projects and programmes in the State are:

- Hospitals Management Board

- Primary Health Care Development Board

- Ondo State Agency for the Control of AIDS

- Emergency Medical Services

- The training Institutions: Schools of Nursing and Midwifery are within the purview of the Department of Nursing Services while the School of Health Technology is under the Department of Public Health.

Figure 6: Organogram of the Health Sector

  - Statement of the sector’s mission, vision and core values

Table 2: Operational Definition of Sector's Core Values

| Core Value | Definition | Examples of Behaviour | Strategy Implications |
| --- | --- | --- | --- |
| Professionalism | Professional excellence through prompt innovative, responsive and efficient service delivery Exhibiting expertise, quality and professional ethics in the discharge of assigned duties. | - Skillfulness, competence and proficiency. - Attention to details in all dealings. - Constant strive for optimum effectiveness and efficiency. - Quality service delivery | - Capacity building and effective training. - Provision of relevant and quality working tools as well as conducive work environment. - Effective manpower deployment (i.e. allocating appropriate personnel to jobs). - Effectively apply a results-based performance evaluation system. |
| Teamwork | The act of a group of people working effectively and efficiently together towards a common goal through collaboration, information sharing and productive interactions. Teamwork promotes synergy which enhances productivity. | - Collaboration and cooperation. - Spontaneous sharing of information and best practices - Productive interaction of members of a team to achieve common end. - Interconnectedness. - Interdependence. - Mutual respect. | - Promote teamwork in the Health Sector through appropriate application of a reward and sanction system. - Entrench teamwork as part of the staff code of conduct booklet. - Open door policy to encourage information sharing - Encouraging group tasks as against individual tasks. |
| Transparency & Accountability | Accountable and open in all activities. As an organization that is critically dependent on taxpayers’ money, integrity is essential in the management of the resources entrusted to us. | - Open door policy to encourage openness and transparency. - Frankness in a constructive manner in dealing with others. - Honesty in all dealings with everyone. - Doing what you say and saying what you mean and feel. - Transparency and openness | - Institute best management practices and systems in the Health Sector (financial, HR, facilities) to facilitate the demonstration of integrity. - Demonstrate zero tolerance to lapses relating to lack of integrity on the part of any member of staff through appropriate use of rewards and sanctions in relation to integrity. |
| Fairness | Ensuring Gender Equity (i.e. being fair to women and men according to their respective needs); and Gender Equality (i.e. equally valuing the similarities and differences of men and women, and the roles they play as partners in their homes, communities and societies) Practical demonstration of gender equity and equality manifests in equality under the law, equal opportunity and equal access to human, financial and other productive resources | - Accountability to all constituent parts of Ondo State’s population. - Ensuring equity and equality in the treatment of men and women in service delivery in the Health sector. | - Explicitly publicize that Ondo State Health Sector is an equal opportunity organization and act accordingly always. - Avoid discrimination in service delivery to men and women. |
| Responsiveness | Responsive to our environment and technologically driven | - Reacting quickly and in a positive manner - Reacting with interest and enthusiasm | - Organization have to be responsive to citizens needs |

Source: Ministry of Health

  - Sector Policy

The aim of the State is to reduce the burden of diseases on the people to enable them live an economic and socially productive life; meet national targets on the elimination and eradication of diseases; and significantly increase the life expectancy and quality of life of the citizen.

Specifically, the review provided bases for the following elements of the MTSS:

- Goals and programmes setting;

- Projects specification;

- Key performance measures; and

- Targets, Outputs and Outcomes.

  - The sector’s goals and programmes for the MTSS period

This section presents brief description of the respective goals and programmes of Health sector. These will be done under the 8 Thematic strategic priority areas itemized below.

- Leadership & Governance

- Health Service Delivery

- Human Resources for Health

- Financing for Health

- Health Information System

- Community Participation

- Partnerships for Health

- Research for Health

Table 3: Summary of State Level Goals, Sector Level Goals, Programmes and Outcomes

| State Level Goal | Sector Level Goal | Programme | Outcome |
| --- | --- | --- | --- |
| To reduce the burden of diseases on the people to enable them live an economic and socially productive life; meet national targets on the elimination and eradication of diseases; and significantly increase the life expectancy and quality of life of the citizen. | GOAL 1: To create and sustain an enabling environment for the delivery of quality health care and development in Ondo State | Health Policy planning | Improved policy direction for the health development |
|  |  | Health legislation and regulation | Strengthened Legislative and Regulatory Functions of Government for Health Development |
|  |  | Accountability, transparency and responsiveness of the health system | Strengthened accountability, transparency and responsiveness of the State health system |
|  |  | State health system performance improvement | Improved the performance of the State Health System implemented by the State health sector |
|  | GOAL 2: To revitalize integrated service delivery towards a quality, equitable and sustainable healthcare | Universal access to essential package of care | Ensured universal access to an essential package of care |
|  |  | Access to health care services | Increased access to health care services |
|  |  | Quality of health care services | Improved the quality of health care service |
|  |  | Demand for health care services | Increased demand for health care services |
|  |  | Financial access for vulnerable groups | Provided financial access especially for the vulnerable groups |
|  | GOAL 3: To plan and implement strategies to address the human resources for health needs in order to enhance its availability as well as ensure equity and quality of health care | Comprehensive policies and plans for HRH for health development | Formulated comprehensive policies and plans for HRH for health development |
|  |  | Framework for objective analysis, implementation and monitoring of HRH performance | Provided a framework for objective analysis, implementation and monitoring of HRH performance |
|  |  | Institutional framework for human resources management practices (in the health sector) | Strengthened institutional framework for human resources management practices in the health sector |
|  |  | Capacity of training institutions to scale up the production of a critical mass of quality, multipurpose, multi-skilled, gender sensitive and mid-level health workers | Strengthened the capacity of training institutions to scale up the production of a critical mass of quality, multipurpose, multi skilled, gender sensitive and mid-level health workers |
|  |  | Organizational and performance based systems for HRH | Improved organizational and performance based management systems for human resources for health |
|  |  | Partnerships and networks to harness contributions for HRH agenda | Fostered partnerships and networks of stakeholders to harness contributions for human resource for health agenda |
|  | GOAL 4: To ensure that adequate and sustainable funds are available and allocated for accessible, affordable, efficient and equitable health care provision and consumption at local and State levels | Implementing Health Financing strategies | Improved Health financing strategies implemented at State and Local levels consistent with the State Health Financing Policy |
|  |  | Protection from medical financial catastrophe and impoverishment | Protection of people from financial catastrophe and impoverishment as a result of using health services |
|  |  | Sustainable funding of healthcare goals and objectives at all levels | Secured level of funding needed to achieve desired health development goals and objectives at all levels in a sustainable manner |
|  |  | Efficiency and equity in the allocation and use of health sector resources at all levels | Efficient and equitable allocation and use of health sector resources at all levels |
|  | GOAL 5: To contribute to an effective National Health Management Information System (NHMIS) to be used as a management tool for informed decision making at all levels for improved health care | Data collection and transmission | Improved data collection and transmission |
|  |  | Infrastructure support and ICT for health databases | Provision of infrastructural support and ICT of health databases and staff training |
|  |  | Sub-Systems in Health Information System | Strengthened sub-systems in the Health Information System |
|  |  | NHMIS Monitoring and Evaluation | Good monitoring and Evaluation of the NHMIS |
|  |  | Health Information Data Analysis and Dissemination | Strengthened analysis of data and dissemination of health information |
|  | GOAL 6: To attain effective community participation in health development and management, as well as community ownership of sustainable health outcomes | Community participation in health development | Strengthened community participation in health development |
|  |  | Community ”ownership” of health services | Empowered communities with skills for positive health actions |
|  |  | Community health services linkages | Strengthened community - health services linkages |
|  | GOAL 7: To enhance harmonized implementation of essential health services in line with national health policy goals | Introduction of collaborative mechanisms for involving all partners in the development and sustenance of the health sector | Collaborative mechanisms are put in place for involving all partners in the development and sustenance of the health sector |
|  | GOAL 8: To utilize research to inform policy, programming, improve health, achieve nationally and internationally health related development goals and contribute to the global knowledge platform | Research and knowledge management systems at all levels of government | Strengthened stewardship role of governments at all levels for research and knowledge management systems |
|  |  | Institutional capacities to promote, undertake and utilize research for evidence— based policy making in health at all levels | Institutional capacities to promote, undertake and utilise research for evidence based policy making in health at all levels strengthened |
|  |  | Comprehensive repository for health research at all levels (including public and non-public sectors | Developed comprehensive repository for health research at all levels (including both public and non-public sectors) |

Table 4: Goals, programmes and outcome deliverables

| Goal | Programme | Outcome Deliverable | Performance indicator | baseline | Annual Actual | Mid-Team Target | Terminal Target |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 2015 | 2017 | 2018 | 2019 |  |
| PRIORITY AREA 1: LEADERSHIP AND GOVERNANCE FOR HEALTH |  |  |  |  |  |  |  |  |
| GOAL 1: To create and sustain an enabling environment for the delivery of quality health care and development in Ondo State | Health Policy planning | Improved policy direction for the health development | Percentage of stakeholders in Ondo State Health sector that are informed regarding the health development policy directives and whose programmes are derived from the SSHDP | 50% | 60% | 70% | 75% |  |
|  | Health legislation and regulation | Strengthened Legislative and Regulatory Functions of Government for Health Development | Percentage of health service providers that are operating within their respective regulatory health laws | 50% | 60% | 70% | 80% |  |
|  | Accountability, transparency and responsiveness of the health system | To strengthen accountability, transparency and responsiveness of the State health system | % of annual facility utilization |  |  |  |  |  |
|  | State health system performance improvement | To improve the performance of the State Health System implemented by the State health sector | % of recommendations from annual programme reviews | 0% |  |  |  |  |
| PRIORITY AREA 2: HEALTH SERVICES DELIVERY |  |  |  |  |  |  |  |  |
| GOAL 2: To revitalize integrated service delivery towards a quality, equitable and sustainable healthcare | Universal access to essential package of care | To ensure universal access to an essential package of care | Percentage of wards with a functional PHC facility providing minimum essential health care package |  | 80% | 90% | 100% |  |
|  | Access to health care services | To increase access to health care services | % of the population within 30mins walk or 5km of a health service |  |  |  |  |  |
|  | Quality of health care services | To improve the quality of health care service | Proportion of registered TB cases cured under DOTS |  | 69.00% | 75.00% | 80.00% |  |
|  | Demand for health care services | To increase demand for health care services | Annual total outpatient attendance in secondary and tertiary health facilities in the State (5% annual increase) |  |  |  |  |  |
|  | Financial access for vulnerable groups | To provide financial access especially for the vulnerable groups | % of identified vulnerable people given access to health services free of charge | TBD | TBD | 100% | 100% |  |
| Priority Area 3: HUMAN RESOURCES FOR HEALTH |  |  |  |  |  |  |  |  |
| GOAL 3: To plan and implement strategies to address the human resources for health needs in order to enhance its availability as well as ensure equity and quality of health care | Comprehensive policies and plans for HRH for health development | To formulate comprehensive policies and plans for HRH for health development | Ratio of Health Professionals per population |  | TBD |  |  |  |
|  | Framework for objective analysis, implementation and monitoring of HRH performance | To provide a framework for objective analysis, implementation and monitoring of HRH performance | % of all Department & Agencies utilizing a standardized monitoring tool for HRH performance | 0% | 0% | 100% | 100% |  |
|  | Institutional framework for human resources management practices (in the health sector) | Strengthen the institutional framework for human resources management practices in the health sector | % of State health facilities with recommended HRH complement as per service delivery demands | TBD |  |  |  |  |
|  | Capacity of training institutions to scale up the production of a critical mass of quality, multipurpose, multi-skilled, gender sensitive and mid-level health workers | To strengthen the capacity of training institutions to scale up the production of a critical mass of quality, multipurpose, multi skilled, gender sensitive and mid-level health workers | No. of Mid-level health workers trained per Health training institution per year | TBD |  |  |  |  |
|  | Organizational and performance based systems for HRH | To improve organizational and performance based management systems for human resources for health | % of Departments and Agencies that have implemented performance-based management systems |  | 100% | 100% | 100% |  |
|  | Partnerships and networks to harness contributions for HRH agenda | To foster partnerships and networks of stakeholders to harness contributions for human resource for health agenda |  |  |  |  |  |  |
| Priority Area 4: FINANCING FOR HEALTH |  |  |  |  |  |  |  |  |
| GOAL 4: To ensure that adequate and sustainable funds are available and allocated for accessible, affordable, efficient and equitable health care provision and consumption at local and State levels | Implementing Health Financing strategies | Improve Health financing strategies implemented at State and Local levels consistent with the State Health Financing Policy | % of the State’s budget allocated to the Health Sector. | 3.20% | 7.00% | 12% | 15% |  |
|  | Protection from medical financial catastrophe and impoverishment | To ensure that people are protected from financial catastrophe and impoverishment as a result of using health services | % of Ondo State Indigenes covered by any financial protection mechanism | TBD |  |  |  |  |
|  | Sustainable funding of healthcare goals and objectives at all levels | To secure a level of funding needed to achieve desired health development goals and objectives at all levels in a sustainable manner | % of total required/needed funds actually allocated to Health at State level is increased by 10% yearly | TBD |  |  |  |  |
|  | Efficiency and equity in the allocation and use of health sector resources at all levels | To ensure efficiency and equity in the allocation and use of health sector resources at all levels | Health Budget performance at the State level is improved | 38% | 40% | 50% | 60% |  |
| Priority Area 5: NATIONAL HEALTH INFORMATION SYSTEM |  |  |  |  |  |  |  |  |
| GOAL 5: To contribute to an effective National Health Management Information System (NHMIS) to be used as a management tool for informed decision making at all levels for improved health care | Data collection and transmission | To improve data collection and transmission | Percentage of health facilities making routine ,timely and complete monthly NHMIS returns to the State level |  |  |  |  |  |
|  | Infrastructure support and ICT for health databases | To provide infrastructural support and ICT of health databases and staff training | Proportion of LGAs using customized data management software (DHIS) | 0% |  |  |  |  |
|  | Sub- Systems in Health Information System | To strengthen sub-systems in the Health Information System | Availability Annual HMIS Data Audit Review Report | none |  |  |  |  |
|  | NHMIS Monitoring and Evaluation | To monitor and evaluate the NHMIS | % of programmes due for outcome/impact evaluation that had evaluation conducted using NHMIS data | 0% |  |  |  |  |
|  | Health Information Data Analysis and Dissemination | To strengthen analysis of data and dissemination of health information | Department s and Agencies that disseminate statistical progress reports periodically | TBD |  |  |  |  |
| Priority Area 6: COMMUNITY PARTICIPATION AND OWNERSHIP |  |  |  |  |  |  |  |  |
| GOAL 6: To attain effective community participation in health development and management, as well as community ownership of sustainable health outcomes | Community participation in health development | To strengthen community participation in health development | Number of quarterly/annual State level fora to engage community leaders and CBOs |  |  |  |  |  |
|  | Community ”ownership” of health services | To empower communities with skills for positive health actions | % of CSOs and community leaders trained and engaging with the government health system | 0% |  | 5% | 20% |  |
|  | Community health services linkages | To strengthen the community - health services linkages | % of public health facilities that have active Committees that include community representatives |  |  |  |  |  |
| Priority Area 7: PARTNERSHIPS FOR HEALTH |  |  |  |  |  |  |  |  |
| GOAL 7: To enhance harmonized implementation of essential health services in line with national health policy goals | Introduction of collaborative mechanisms for involving all partners in the development and sustenance of the health sector | To ensure that collaborative mechanisms are put in place for involving all partners in the development and sustenance of the health sector | Existence of a joint / integrated operational work plan | none |  | yes | Yes |  |
| Priority Area 8: RESEARCH FOR HEALTH |  |  |  |  |  |  |  |  |
| GOAL 8: To utilize research to inform policy, programming, improve health, achieve nationally and internationally health related development goals and contribute to the global knowledge platform | Research and knowledge management systems at all levels of government | To strengthen the stewardship role of governments at all levels for research and knowledge management systems | % of health budget spent on health research and evaluation at State Level | TBD |  |  |  |  |
|  | Institutional capacities to promote, undertake and utilize research for evidence— based policy making in health at all levels | To build institutional capacities to promote, undertake and utilize research for evidence based policy making in health at all levels | Percentage of government policies and plans that are produced based on results of research and evaluation conducted | 0 | 0% | 20% | 30% |  |
|  | Comprehensive repository for health research at all levels (including public and non-public sectors | To develop a comprehensive repository for health research at all levels (including both public and nonpublic sectors): | % of State Department and Agencies implementing the National Health Research communication Strategy |  |  |  |  |  |

- The Development of Sector Strategy

  - Major Strategic Challenges

Some of the challenges encountered during the development of health sector’s strategy are:

- non availability and poor quality of relevant data;

- limited involvement of other relevant stakeholders;

- inadequate logistics provision;

- poor time management;

- insufficient cohesive system reasoning

  - Resource Constraints

Resource constraints are notable inhibitory factors to the capacity of the sector to implement its financial obligations. The actual budgetary release, as a percentage of the budgetary allocation to the health sector, reflects the resource constraints.

The following are the highlights of the 2015 budget data presented in table 6. The challenges encountered in implementing the 2015 budget are as listed below:

- Drastic reduction in the budget of MDAs e,g (sectoral budget comparison for 2014 and 2015 )

- Reduction in the federal allocation due to fall in price of crude oil in the international market

- Non availability of funds as at when needed

Table 5: Summary of 2014 Budget Data for the Sector

| Item | Approved Budget (N) in 2014 | Amount Released (N) in 2014 | Actual Expenditure (N) in 2014 | Amount Released as % of Approved | Actual Expenditure as % of Releases |
| --- | --- | --- | --- | --- | --- |
| Personnel | 8,552,170,632.28 | 7,500,417,926.58 | 7,500,417,926.58 | 87.7% | 100% |
| Overhead | 110,700,000.00 | 45,987,500.00 | 45,987,500.00 | 41.50% | 100% |
| Capital | 7,112,464,000.00 | 1,811,307,836.52 | 1,811,307,836.52 | 25.50% | 100% |
| Total | 15,775,334,632.28 | 9,357,713,263.10 | 9,357,713,263.10 | 59.3% | 100% |

Table 6: Summary of 2015 Budget Data for the Sector

| Item | Approved Budget (N) in 2015 | Amount Released (N) in 2015 | Actual Expenditure (N) in 2015 | Amount Released as % of Approved | Actual Expenditure as % of Releases |
| --- | --- | --- | --- | --- | --- |
| Personnel | 9,048,342,518.69 | 7,430,933,327.13 | 7,430,933,327.13 | 82.1% | 100% |
| Overhead | 90,300,000.00 | 61,392,900.00 | 61,392,900.00 | 68.0% | 100% |
| Capital | 3,575,000,000.00 | 1,484,339,345.50 | 1,484,339,345.50 | 41.5% | 100% |
| Total | 12,713,642,518.69 | 1,976,000,345.37 | 1,976,000,345.37 | 17.2% | 100% |

Table 7: Summary of 2016 Budget Data for the Sector (Jan-April/May 2016)

| Item | Approved Budget (N) in 2016 | Amount Released (N) as at end April 2016 | Actual Expenditure (N) as at end April 2016 | Amount Released as % of Approved | Actual Expenditure as % of Releases |
| --- | --- | --- | --- | --- | --- |
| Personnel | 8,840,536,540.11 | 2,750,091,160.33 | 2,750,091,160.33 | 31.10% | 31.10% |
| Overhead | 57,500,000.00 | 22,100,000.00 | 22,100,000.00 | 38.44% | 38.44% |
| Capital | 5,002,200,000.00 | 936,385,140.90 | 936,385,140.90 | 18.7% | 18.7% |
| Total | 13,900,236,540.11 | 3,708,576,301.23 | 3,708,576,301.23 | 26.68% | 26.68% |

Table 8: Summary of the Review of Ongoing and Existing Projects Scorecard (Ranked by Average score for Ongoing and Existing Projects and by Final Score for New Projects)

| S/N | Project Title | Criterion 1 | Criterion 2 | Criterion 3 | Criterion 4 | Criterion 5 | Average / Final Score | Rank | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ongoing Projects |  |  |  |  |  |  |  |  |  |
| 1 | Care and Support of People Infected and Affected by HIV/AIDS | 4 | 4 | 4 | 4 | 4 | 4 | 1 | Poor socio-economic impact indices as a result of poor home based care |
| 2 | Coordination meeting platforms( SACA-LACA, SACA-CSO, SACA-LM, Biannual meeting) | 4 | 4 | 4 | 4 | 4 | 4 | 1 | Weak coordination at various levels. |
| 3 | Medical Assistance to Federal Medical Centre ,Owo | 4 | 4 | 4 | 4 | 3 | 3.8 | 3 |  |
| 4 | HIV Counseling and Testing | 4 | 4 | 3 | 4 | 4 | 3.8 | 3 | Inadequate HCT sites especially at the rural area & Low uptake of HCT |
| 5 | Condom Promotion | 4 | 4 | 4 | 4 | 3 | 3.8 | 3 | Required for supply of condoms to employees at government, industrial offices & Required for MPPI for outreaches in the state |
| 6 | Women and men in need of HIV treatment receive treatment | 4 | 4 | 4 | 4 | 3 | 3.8 | 3 | Positive pregnant women are lost to TBAs. Low knowledge on PMTCT. Low condom use. |
| 7 | Construction of Hostels for Schools of Nursing | 4 | 4 | 4 | 4 | 3 | 3.8 | 3 | To meet up with the Requirement of N&MCN for Accreditation of the School |
| 8 | Payment of Allowance for Guest Lecturers (SoN) | 4 | 4 | 4 | 4 | 3 | 3.8 | 3 | Enhances Students’ Knowledge & Skills in different Specialties of Practice |
| 9 | Library (Journals) | 4 | 4 | 4 | 4 | 3 | 3.8 | 3 | Updating of Students Knowledge on New trends |
| 10 | Provision of Office Furniture & Internet Services for SON | 4 | 4 | 4 | 4 | 3 | 3.8 | 3 | Conducive Working Environment for Teachers & Availability of Internet for Students |
| 11 | Accreditation exercises for School of health Tech | 4 | 4 | 4 | 4 | 3 | 3.8 | 3 | Prerequisite for admission of new students |
| 12 | External works at Mother and Child Hospital, Ondo (Completed but not paid) | 4 | 4 | 3 | 4 | 3 | 3.6 | 12 |  |
| 13 | Construction of Medical Ward at Trauma and Surgical Centre Ondo | 4 | 4 | 4 | 3 | 3 | 3.6 | 12 | For a comprehensive management of medical cases as a prerequisite for accreditation as Teaching Hospital |
| 14 | Upgrading of Comprehensive Health Centre, Araromi-Obu to General Hospital | 4 | 4 | 3 | 4 | 3 | 3.6 | 12 | To increase accessibility and referral services |
| 15 | Construction of Science Laboratory for the Schools of Nursing and Midwifery | 4 | 4 | 3 | 4 | 3 | 3.6 | 12 | To meet up with the Requirement of N&MCN for Accreditation of the School |
| 16 | Trauma and surgical Centre | 4 | 4 | 4 | 3 | 3 | 3.6 | 12 | To cope with influx of referrals |
| 17 | Task force on Counterfeit and Fake drugs | 4 | 4 | 4 | 2 | 4 | 3.6 | 12 | To reduce circulation of counterfeit drugs |
| 18 | Nursing and Midwifery Council of Nigeria Activities | 4 | 4 | 4 | 2 | 4 | 3.6 | 12 | Monitoring and evaluation |
| 19 | Emergency Preparedness and Disease Surveillance | 4 | 4 | 4 | 2 | 4 | 3.6 | 12 | To improve the state capacity to manage emerging disease outbreak |
| 20 | Facility based Records (Data Mop-up) | 4 | 4 | 4 | 2 | 4 | 3.6 | 12 | To strengthen data management |
| 21 | Confidential Enquiry into Maternal Death | 4 | 4 | 4 | 2 | 4 | 3.6 | 12 | To track the causes of maternal death and improve response |
| 22 | Nigeria State Health Investment Project Credit (World Bank Assisted) | 4 | 4 | 4 | 3 | 3 | 3.6 | 12 | To improve quantity and quality of health service delivery |
| 23 | Printing of Health Management Information System data tools | 4 | 3 | 4 | 3 | 4 | 3.6 | 12 | To ensure effective data management |
| 24 | Community Medicine | 4 | 4 | 4 | 2 | 4 | 3.6 | 12 | To enhance public health activities |
| 25 | Communications | 3 | 4 | 4 | 4 | 3 | 3.6 | 12 | Behavior change communication out of stock & Poor comprehensive knowledge of HIV/AIDS |
| 26 | Prevention of Biomedical Transmission of HIV | 4 | 4 | 3 | 4 | 3 | 3.6 | 12 | Positive pregnant women are lost to TBAs. Low knowledge on PMTCT. Low condom use. |
| 27 | Policy, Advocacy, Human Rights, and Legal Issues | 4 | 4 | 3 | 4 | 3 | 3.6 | 12 | There is no anti-stigma law (anti-stigma law it has passed second reading in the state house of assembly). |
| 28 | Human resources (capacity building) | 4 | 4 | 3 | 4 | 3 | 3.6 | 12 | Some staff have retired. New and old staff should be trained on current updates. |
| 29 | Financial Resources | 4 | 4 | 3 | 4 | 3 | 3.6 | 12 | Irregular release of fund to LACAs & MDAs for HIV activities. |
| 30 | Monitoring and Evaluation, Research and Knowledge Management | 4 | 4 | 4 | 3 | 3 | 3.6 | 12 | There is need for regular capacity building for data collection and report of activities been carried out |
| 31 | Accreditation of School of Midwifery and other activities of N&MCN | 4 | 4 | 2 | 4 | 4 | 3.6 | 12 | To lift embergo on students admission |
| 32 | Completion of Modern Laboratory | 4 | 4 | 3 | 4 | 3 | 3.6 | 12 | Enhances Better Practical experienceStudents |
| 33 | Procurement of Reagents/Consumables | 4 | 4 | 3 | 4 | 3 | 3.6 | 12 | Enhances Better Practical experience Students |
| 34 | Procurement of laboratory Chemicals, reagents& consumables School of health Tech | 4 | 4 | 3 | 4 | 3 | 3.6 | 12 | Enhances Better Practical experience Students |
| 35 | Additional jobs on the construction of Accident and Emergency Hospital Complex at Trauma Centre Ondo | 3 | 4 | 3 | 4 | 3 | 3.4 | 35 | To cope with influx of referrals |
| 36 | Festival of Surgery; Eye Camp at the MEC | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | To assist the indigent patients |
| 37 | Medical Board of Enquiry and Medical Assistance | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | For medical evaluation and requisite medical assistance |
| 38 | Activities of the Medical and Dental Council of Nigeria | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | To maintain standard of practice and ethics |
| 39 | HIV/AIDS Prevention and control/rehabilitation programme for people living with HIV/AIDS | 4 | 4 | 3 | 2 | 4 | 3.4 | 35 | To reduce incidence and improve treatment and care of HIV/AIDS cases |
| 40 | Inspection of Pharmaceutical premises and patient Medicine shops | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | To maintain standard of practice and ethics |
| 41 | Pharmacists Council of Nig. Activities | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | To regulate Pharmaceutical practice |
| 42 | Monitoring and Evaluation of Nursing Services | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | To regulate standard of practice |
| 43 | Nigeria State Health Investment Programme DLI Re-imbursement | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | To enhance effective service delivery |
| 44 | Provision for 1 year mandatory community experience for 50 basic students midwives for maternal & child care | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | To improve maternal and child care |
| 45 | Neonatal Intensive Nursing Training Programme | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | To improve Neonatal service |
| 46 | Free Health Drugs | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | To enhance drug accessibility |
| 47 | Ondo State Health Statistics bulletin | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | For information dissemination |
| 48 | Meetings of State/ National Council on Health | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | For holistic health care policy formulation |
| 49 | Accreditation Visit N and MC | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | To lift embargo on students admission |
| 50 | Safe motherhood project-scaling up of Abiye | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | To improve maternal and child health |
| 51 | National Council on Health | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | For holistic health care policy formulation |
| 52 | Prevention of Mother to Child Transmission of HIV(PMTCT) | 3 | 4 | 3 | 4 | 3 | 3.4 | 35 | Inadequate HCT sites, & Low uptake of PMTCT especially at the rural area |
| 53 | Construction of hostels for School of Nursing and Midwifery | 4 | 4 | 3 | 3 | 3 | 3.4 | 35 | To meet up with the Requirement of N&MCN for Accreditation of the School |
| 54 | Procurement of anatomical models for demonstration rooms of the school | 4 | 4 | 3 | 3 | 3 | 3.4 | 35 | To enhance teaching/learning process |
| 55 | Management and Maintenance of Mother and Child Hospital and Other Health Facilities | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | To enhance service delivery |
| 56 | Maintenance of inmate of Ago-Ireti | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | To assist the inmates |
| 57 | Assistance towards Medical Treatment | 4 | 4 | 4 | 2 | 3 | 3.4 | 35 | To give support to indigents |
| 58 | Landscaping and beautification of Laje Road Ondo (Access road to Medical Village) | 4 | 4 | 3 | 3 | 2 | 3.2 | 58 | To provide a conducive environment |
| 59 | Construction of Surgical Ward extension and Physiotherapy Unit at Trauma Centre Ondo | 3 | 4 | 2 | 4 | 3 | 3.2 | 58 | To cope with influx of referrals |
| 60 | Construction of Alaanu Hostel, Medical Village Ondo | 4 | 4 | 2 | 4 | 2 | 3.2 | 58 | To provide accommodation for patient relatives |
| 61 | Accrediation and Registration of Private Health Facilities | 4 | 4 | 3 | 2 | 3 | 3.2 | 58 | To ensure provision of quality health care services |
| 62 | Roll back malaria | 3 | 4 | 3 | 2 | 4 | 3.2 | 58 | For prevention and control of malarial infection |
| 63 | TBL Control Programme | 4 | 4 | 2 | 2 | 4 | 3.2 | 58 | For prevention and control of TBL |
| 64 | Non-communicable Diseases | 4 | 4 | 3 | 2 | 3 | 3.2 | 58 | For prevention and control of non-communicable diseases |
| 65 | Publicity | 3 | 4 | 4 | 2 | 3 | 3.2 | 58 | Health promotion and awareness |
| 66 | Staff Training | 4 | 4 | 2 | 2 | 4 | 3.2 | 58 | To enhance efficiency and effectiveness |
| 67 | IGR Tracking | 4 | 4 | 3 | 2 | 3 | 3.2 | 58 | To monitor revenue generation |
| 68 | Renovation of block 11 at GH, Idanre | 4 | 2 | 4 | 4 | 2 | 3.2 | 58 | To improve capacity to manage inpatient cases |
| 69 | Health Education and Social Mobilisation | 4 | 3 | 4 | 2 | 3 | 3.2 | 58 | Health promotion and awareness and to enhance community participation |
| 70 | Maternal, Newborn and Child Health week | 4 | 3 | 4 | 2 | 3 | 3.2 | 58 | To improve maternal, newborn and child health services |
| 71 | Non-communicable diseases (Guinea worm) | 4 | 3 | 4 | 2 | 3 | 3.2 | 58 | For prevention and control of Guinea worm |
| 72 | HIV/AIDS | 4 | 3 | 4 | 2 | 3 | 3.2 | 58 | To prevent and control HIV/AIDS |
| 73 | Onchocerciasis | 4 | 3 | 4 | 2 | 3 | 3.2 | 58 | To prevent and control Onchocerciasis |
| 76 | Midwifery service scheme/SURE-P | 4 | 3 | 4 | 2 | 3 | 3.2 | 58 | To improve maternal and child services |
| 77 | Reproductive Health/Family Planning | 4 | 3 | 4 | 2 | 3 | 3.2 | 58 | To improve maternal health |
| 78 | National programme for Immunization (ORIREWA) | 4 | 3 | 4 | 2 | 3 | 3.2 | 58 | To improve immunization services |
| 80 | Schistosomiasis | 4 | 3 | 4 | 2 | 3 | 3.2 | 58 | To prevent and control Schistosomiasis |
| 81 | Nutrition | 4 | 4 | 3 | 2 | 3 | 3.2 | 58 | To improve nutritional support services |
| 82 | Institutional Arrangement and Coordination Mechanism | 4 | 4 | 2 | 4 | 2 | 3.2 | 58 | Irregular release of fund to LACAs & MDAs for Proper coordination of preventive activities |
| 83 | Procurement & logistics supply | 4 | 4 | 2 | 4 | 2 | 3.2 | 58 | Stock out of commodities has affected uptake of HIV services. |
| 84 | Basic Laboratory Equipment; and other Medical Equipment | 4 | 4 | 3 | 1 | 3 | 3 | 84 | To improve medical service |
| 85 | Counterpart Fund (NHIS) | 2 | 4 | 3 | 3 | 3 | 3 | 84 | To provide support for health service delivery |
| 86 | Printing of Free Health Cards | 4 | 4 | 3 | 2 | 2 | 3 | 84 | To provide free health service to under-5 children |
| 87 | Purchase of office equipment | 4 | 4 | 3 | 2 | 2 | 3 | 84 | To improve health care administration |
| 88 | Health Insurance for Primary School Pupils Counterpart Contribution | 3 | 4 | 3 | 2 | 3 | 3 | 84 | To provide support for health service delivery |
| 90 | Renovation of existing facilities / Procurement of consumables (SoM) | 3 | 4 | 2 | 3 | 3 | 3 | 84 | To enhance learning |
| 91 | Payment of allowance for guest lecturers (SoM) | 4 | 4 | 2 | 3 | 2 | 3 | 84 | Enhances Students’ Knowledge & Skills in different Specialties of Practice |
| 92 | upgrading of facilities for the School of Nursing and Midwifery | 2 | 4 | 3 | 3 | 3 | 3 | 84 | Adds Aesthetic value to school environment |
| 93 | Completion of Igbotako General Hospital | 4 | 4 | 2 | 1 | 3 | 2.8 | 93 | To improve service delivery |
| 94 | Population Activities | 2 | 4 | 3 | 2 | 3 | 2.8 | 93 | For community mapping, planning and public health intervention |
| 95 | Public Health Laboratory | 2 | 4 | 3 | 2 | 3 | 2.8 | 93 | To improve the diagnostic capacity for diseases of public health importance |
| 96 | Renovation of children ward, SSHO | 4 | 2 | 2 | 4 | 2 | 2.8 | 93 | To improve inpatient care |
| 97 | Health Rangers | 3 | 3 | 3 | 2 | 3 | 2.8 | 93 | To improve facility utilization |
| 98 | School Health service | 3 | 3 | 3 | 2 | 3 | 2.8 | 93 | To provide school health services |
| 99 | Updating of teachers by N&MCN | 4 | 4 | 2 | 2 | 2 | 2.8 | 93 | Capacity Building Towards Effective Service Delivery |
| 100 | Procurement and equipment of the sick-bay | 4 | 4 | 2 | 2 | 2 | 2.8 | 93 | Prompt health care services to students |
| 101 | Procurement of reagents/ consumables | 3 | 4 | 2 | 3 | 2 | 2.8 | 93 | Better Performance of Students in Practical Aspects |
| 102 | Procurement of library books School of health Tech | 4 | 3 | 2 | 3 | 2 | 2.8 | 93 | Updating of Students Knowledge on New Trends |
| 103 | Central Blood Transfusion Services | 3 | 4 | 1 | 2 | 3 | 2.6 | 103 | To promote safe blood transfusion |
| 105 | International Travel Control Unit | 2 | 4 | 3 | 2 | 2 | 2.6 | 103 | To certify health status of intending travelers |
| 106 | Construction and Expansion of Equipment Stores and Traditional Medicine Board Offices, Oke-Eda | 1 | 4 | 3 | 2 | 3 | 2.6 | 103 | To enhance medical equipment storage capacity and to regulate activities of traditional medical practitioners |
| 107 | Integrated supportive supervision | 3 | 2 | 3 | 2 | 3 | 2.6 | 103 | For effective monitoring and evaluation of health service delivery. |
| 108 | Security and cleaning of secretariat complex | 2 | 2 | 3 | 2 | 3 | 2.4 | 108 | For conducive administrative environment |
| 109 | General services | 2 | 2 | 3 | 2 | 3 | 2.4 | 108 | For maintainnce |
| 110 | Annual World Health Day | 3 | 2 | 3 | 2 | 2 | 2.4 | 108 | To create health awareness |
| 111 | Monitoring/Quaterly Board Meetings/ Monthly Technical Review meetings | 3 | 2 | 3 | 2 | 2 | 2.4 | 108 | For effective coordination of health services. |
| 113 | District Health Management Information System | 3 | 2 | 3 | 2 | 2 | 2.4 | 108 | To improve data quality and management. |
| 115 | Procurement of Dental Chair for School of health Tech | 2 | 2 | 3 | 2 | 2 | 2.2 | 115 | To improve quality of training for dental service. |
| 116 | Florence Nightingale Speech Contest | 2 | 1 | 2 | 2 | 3 | 2 | 116 | Stimulates Healthy Educational Interactions among the Students |
| 117 | Provision of Sporting Facilities & NISONMG | 2 | 1 | 2 | 2 | 3 | 2 | 116 | Stimulates Sporting Interactions among all Students of Schools of Nursing in Nigeria |
| 118 | Updating of Teachers by Nursing & Midwifery Council | 2 | 1 | 3 | 2 | 1 | 1.8 | 118 | Capacity Building Towards Effective Service Delivery |

| S/N |  | Project Title | Criterion 1 |  | Criterion 2 |  | Criterion 3 |  |  | Criterion 4 | Criterion 5 |  |  | Average / Final Score |  | Rank |  | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| New Projects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | 3 nos of incinerators |  |  | NA |  | NA |  | NA | NA |  |  | 4 | 4 |  | 1 |  | For health Service Delivery |  |
| 2 | Maintenance and support of call centre, cost system, wide line, bandwith, subscription, Toll-Free lines |  |  | NA |  | NA |  | NA | NA |  |  | 4 | 4 |  | 1 |  | For prompt emergency surveillance and response |  |
| 3 | Accreditation of SON |  |  | NA |  | NA |  | NA | NA |  |  | 4 | 4 |  | 1 |  | Lifting of embargo on students admission |  |
| 4 | Re-Roofing of Classrooms (SoN) |  |  | NA |  | NA |  | NA | NA |  |  | 4 | 4 |  | 1 |  | Conducive learning environment for students |  |
| 5 | Construction of Mother and Child Hospital, Ikare |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | To Increase coverage for maternal and child health Service |  |
| 6 | Construction of Mother and Child Hospital, Okitipupa |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | To Increase coverage for maternal and child health Service |  |
| 7 | Renovation and upgrading of Secondary Facilities |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | Improved Health Service Delivery |  |
| 8 | Construction of Public Health Laboratory,OkeEda ,Akure |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | For improved health Service Delivery |  |
| 9 | Logistics Management and Coordinating Unit (LMCU) |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | For improved health Service Delivery |  |
| 10 | Health Insurance for Primary School Pupils |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | Health Service coverage and reducing out of pocket expenses for school pupils |  |
| 11 | Procurement of one number public address system vehicle |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | For sensitization and awareness |  |
| 12 | Construction of additional Base Station at Igbado |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | Improved coverage around the state |  |
| 13 | EMS Vehicle Sticker Printing and Deployment |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | For publicity |  |
| 14 | Supply of Ambulance, Extrication Vehicle and Towing Truck for the Igbado Base Station |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | For Improved emergency response system |  |
| 15 | Computerized Web Based EMS Management System(Inventory Management System, Trauma Registry and Personnel Management System) |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | For Improved data compilation of human resources for health |  |
| 16 | Construction of school clinic and school store (SoM) |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | For prompt Health Care service delivery to Students |  |
| 17 | Construction of Sick-Bay for SON |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | For prompt Health Care delivery to Students |  |
| 18 | Re-Roofing of Administrative Block (SoN) |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | Conducive working environment for staff |  |
| 19 | Construction of Students Chairs and lockers School of health Tech |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | Conducive learning environment for staff |  |
| 20 | Construction of New Administrative block School of health Tech |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | Conducive working environment for staff |  |
| 21 | Purchase of 100 double bunk beds School of health Tech |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | To improve learning |  |
| 22 | Teaching Aids for DST |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | To improve learning and skill acquisition |  |
| 23 | Purchase of 3 Hilux Vehicles |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | For improved service delivery |  |
| 24 | Construction / Provision of Office Buildings |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | For conducive environment for employee |  |
| 25 | Rehabilitation / Repair of Office Buildings |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | Health Service Delivery |  |
| 26 | Research and Development |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | To increase research in the state |  |
| 27 | Capacity Building |  |  | NA |  | NA |  | NA | NA |  |  | 3 | 3 |  | 5 |  | Improved Human Resources for Health |  |
| 28 | Establishment of Health Insurance Agency |  |  | NA |  | NA |  | NA | NA |  |  | 2 | 2 |  | 28 |  | To increase universal health coverage |  |
| 29 | 3 nos of Hilux vehicle |  |  | NA |  | NA |  | NA | NA |  |  | 2 | 2 |  | 28 |  | For health Service Delivery |  |
| 30 | 6 nos of ambulance vehicles |  |  | NA |  | NA |  | NA | NA |  |  | 2 | 2 |  | 28 |  | for emergency rescue of victims across the state |  |
| 31 | Reconstruction of cold chain store Okitipupa |  |  | NA |  | NA |  | NA | NA |  |  | 2 | 2 |  | 28 |  | To increase the lifespan of vaccines for improved service delivery |  |
| 32 | 18 nos of Ice liner deep freezers |  |  | NA |  | NA |  | NA | NA |  |  | 2 | 2 |  | 28 |  | To increase the lifespan of vaccines for improved service delivery |  |
| 33 | Construction of Akure administrative office extension including office equipment and Furniture |  |  | NA |  | NA |  | NA | NA |  |  | 2 | 2 |  | 28 |  | Improved conducive environment |  |
| 34 | Drilling of Bore Hole for five Base Station |  |  | NA |  | NA |  | NA | NA |  |  | 2 | 2 |  | 28 |  | For health Service Delivery |  |
| 35 | Purchase of Library textbooks |  |  | NA |  | NA |  | NA | NA |  |  | 2 | 2 |  | 28 |  | Updating of Students Knowledge on New Trends |  |
| 36 | Landscaping & Beautification of the SON & SOM |  |  | NA |  | NA |  | NA | NA |  |  | 2 | 2 |  | 28 |  | Aesthetic learning and working environment |  |
| 37 | Construction of Matron's Quarters for SON |  |  | NA |  | NA |  | NA | NA |  |  | 2 | 2 |  | 28 |  | To meet up with the Requirement of N&MCN for Accreditation of the School |  |
| 38 | Landscaping Beautification of School of health Tech |  |  | NA |  | NA |  | NA | NA |  |  | 2 | 2 |  | 28 |  | Aesthetic learning and working environment |  |
| 39 | Resuscitation of X-Ray Department School of health Tech |  |  | NA |  | NA |  | NA | NA |  |  | 2 | 2 |  | 28 |  | To contribute more to hospital utilization |  |
| 40 | Renovation Re-roofing of present administrative block School of health Tech |  |  | NA |  | NA |  | NA | NA |  |  | 2 | 2 |  | 28 |  | Conducive and cosy environment for staff |  |
| 41 | Procurement of Office furniture School of health Tech |  |  | NA |  | NA |  | NA | NA |  |  | 2 | 2 |  | 28 |  | Conducive and cosy environment for staff |  |
| 42 | Procurement of 1No 40-seater Bus School of health Tech |  |  | NA |  | NA |  | NA | NA |  |  | 2 | 2 |  | 28 |  | Transporting of students during engagement by the school |  |
| 43 | Enlightenment / Awareness |  |  | NA |  | NA |  | NA | NA |  |  | 2 | 2 |  | 28 |  | Health Service Delivery |  |
| 44 | 19 nos of backup generators |  |  | NA |  | NA |  | NA | NA |  |  | 1 | 1 |  | 44 |  | Health Service Delivery |  |

Note:

NA = Not Applicable

Criterion 1= Evidence that the Existing Projects are indeed Ongoing

Criterion 2= Clarity of Current Justification for Budget Commitment

Criterion 3= Current Impact of Budget Commitment

Criterion 4= Likelihood of Completion in 2017 – 2019 Timeframe.

Criterion 5= Relation to the Sector’s goals

Table 9: Capital Costs Commitments

| S/N | Project Title | Status of Completion | Contract Sum (N) | Amount Paid to Date (N) | Outstanding Commitment (N) |
| --- | --- | --- | --- | --- | --- |
| 1. | Care and Support of People Infected and Affected by HIV/AIDS | Ongoing | 5,000,000 |  |  |
| 2. | Coordination meeting platforms( SACA-LACA, SACA-CSO, SACA-LM, Biannual meeting) | Ongoing | 8,000,000 |  |  |
| 3. | Medical Assistance to Federal Medical Centre, Owo | Ongoing | 10,000,000 |  |  |
| 4. | HIV Counseling and Testing | Ongoing | 14,000,000 |  |  |
| 5. | Condom Promotion | Ongoing | 6,500,000 |  |  |
| 6. | Women and men in need of HIV treatment receive treatment |  | 6,500,000 |  |  |
| 7. | Construction of Hostels for Schools of Nursing and Midwifery | Ongoing | 100,000,000.00 | 76,000,000 | 24,000,000.00 |
| 8. | Payment of Allowance for Guest Lecturers (SoN) | Ongoing | 1,650,000.00 | - | 1,650,000.00 |
| 9. | Library (Journals) | Ongoing | 950,000.00 | - | 950,000.00 |
| 10. | Provision of Office Furniture & Internet Services for SON | Ongoing | 1,200,000.00 | - | 1,200,000.00 |
| 11. | Accreditation exercises for School of health Tech |  | 10,000,000 |  |  |
| 12. | Base Station roomy (5 Base Stations and Call Centre) | Ongoing | 3,000,000 |  |  |
| 13. | Maintenance and Support of Call Centre Cost System wide line bandwidth, subscription, Toll free lines | Ongoing | 25,000,000 |  |  |
| 14. | Purchase of diesel for the Call Centre | Ongoing | 2,000,000 |  |  |
| 15. | External works at Mother and Child Hospital, Ondo (Completed but not paid) | Ongoing | 630,809,995.07 | 554,685,494.84 | 76,124,045.23 |
| 16. | Construction of Medical Ward at Trauma and Surgical Centre Ondo | Reviewed | 514,741,450.57 | 302,127,634.87 | 212,613,815.70 |
| 17. | Upgrading of Comprehensive Health Centre, Araromi-Obu to General Hospital |  |  |  |  |
| 18. | Completion of Science Laboratory for the Schools of Nursing and Midwifery | Ongoing | 950,000.00 | 900,000.00 | 50,000.00 |
| 19. | Trauma and surgical centre |  | 2,500,000,000,000 |  |  |
| 20. | Task force on Counterfeit and Fake drugs |  | 1,000,000 |  |  |
| 21. | Nursing and Midwifery Council of Nigeria Activities |  | 1,000,000 |  |  |
| 22. | Emergency Preparedness and Disease Surveillance |  | 100,000,000 |  |  |
| 23. | Facility bases records (Data Mop-up) |  | 2,000,000 |  |  |
| 24. | Confidential Enquiry into Maternal Death |  | 3,500,000 |  |  |
| 25. | Nigeria State Health Investment Project Credit (World Bank Assisted) |  | 4,000,000 |  |  |
| 26. | Printing of Health Management Information System data tools |  |  |  |  |
| 27. | Community Medicine |  | 250,000 |  |  |
| 28. | Commuincations (outreaches and special event) |  | 2,000,000 |  |  |
| 29. | Prevention of Biomedical Transmission of HIV |  | 6,750,000 |  |  |
| 30. | Policy, Advocacy, Human Rights, and Legal Issues |  | 2,000,000 |  |  |
| 31. | Human resources (capacity building) |  | 7,500,000 |  |  |
| 32. | Financial Resources |  | 2,000,000 |  |  |
| 33. | Monitoring and Evaluation, Research and Knowledge Management |  | 10,000,000 |  |  |
| 34. | Accreditation of School of Midwifery and other activities of N&MCN |  | 1,000,000 | 1,000,000 | - |
| 35. | Completion of Modern Laboratory |  | 750,000 |  |  |
| 36. | Procurement of Reagents/Consumables | Ongoing | 950,000.00 | - | 950,000.00 |
| 37. | Procurement of laboratory Chemicals, reagents & consumables School of health Tech |  | 1,000,000 |  |  |
| 38. | Branding and EMS Social Awareness Campaign / Trauma Summit Publicity |  | 10,000,000 |  |  |
| 39. | Base Station fuel upkeep, EMS Consumables |  | 40,000,000 |  |  |
| 40. | Maintenance of Operational Vehicles (Ambulances, Towing Trucks, Extrication and Utility vehicles) |  | 45,000,000 |  |  |
| 41. | Additional jobs on the construction of Accident and Emergency Hospital Complex at Trauma Centre Ondo |  | - |  |  |
| 42. | Festival of Surgery; Eye Camp at the MEC |  | 20,000,000 |  |  |
| 43. | Medical Board of Enquiry and Medical Assistance (Meetings & Investigations) |  | 1,000,000 |  |  |
| 44. | Activities of the Medical and Dental Council of Nigeria |  | 1,000,000 |  |  |
| 45. | HIV/AIDS Prevention and control/rehabilitation programme for people living with HIV/AIDS |  |  |  |  |
| 46. | Inspection of Pharmaceutical premises and patient Medicine shops |  | 1,000,000 |  |  |
| 47. | Pharmacists Council of Nig. Activities |  | 1,000,000 |  |  |
| 48. | Monitoring and Evaluation of Nursing Services |  | 1,000,000 |  |  |
| 49. | Nigeria State Health Investment Programme DLI Re-imbursement |  | 4,000,000 |  |  |
| 50. | Provision for 1 year mandatory community experience for 50 basic students midwives for maternal & child care |  |  |  |  |
| 51. | Neonatal Intensive Nursing Training Programme |  | 2,500,000 |  |  |
| 52. | Free Health Drugs |  | 150,000,000 |  |  |
| 53. | Ondo State Health Statistics bulletin |  | 1,000,000 |  |  |
| 54. | Meetings of State/ National Council on Health |  | 10,000,000 |  |  |
| 55. | Accreditation Visit N and MC | Ongoing | 2,000,000.00 | 1,925,775.00 | 74,225.00 |
| 56. | Safe motherhood project-scaling up of Abiye |  | 50,000,000 |  |  |
| 57. | National Council on Health (OSPHCDB) |  | 500,000 |  |  |
| 58. | Prevention of Mother to Child Transmission of HIV(PMTCT) |  | 6,750,000 |  |  |
| 59. | Construction of hostels for School of Nursing and Midwifery |  | 100,000,000 |  |  |
| 60. | Procurement of anatomical models for demonstration rooms of the school |  | 1,000,000 |  |  |
| 61. | Management and Maintenance of Mother and Child Hospital and Other Health Facilities |  | 280,000,000 | 162,558,760.86 | 117,441,239.14 |
| 62. | Maintenance of inmate of Ago-Ireti |  | 20,000,000 | 11,970,000.00 | 8,030,000 |
| 63. | Assistance towards Medical Treatment |  | 50,000,000 | 45,847,400.00 | 4,152,600 |
| 64. | Capacity Building (EMS) |  | 10,000,000 |  |  |
| 65. | Rehabilitation/repairs –housing |  |  |  |  |
| 66. | Landscaping and beautification of Laje Road Ondo (Access road to Medical Village) | Ongoing | 92,576,098.44 | 52,625,237.14 | 39,950,086.13 |
| 67. | Construction of Surgical Ward extension and Physiotherapy Unit at Trauma Centre Ondo | Built and Transfer Arrangement | 1,017,688,682.03 | Nil | Nil |
| 68. | Construction of Alaanu Hostel, Medical Village Ondo |  | 327,356,516.92 | 106,865,837.72 | 220,490,979.20 |
| 69. | Accrediation and Registration of Private Health Facilities |  | 2,000,000 |  |  |
| 70. | Roll back malaria (MoH& OSPHCDB) |  | 500,000.00 |  |  |
| 71. | TBL Control Programme |  | 1,000,000.00 |  |  |
| 72. | Non-communicable Diseases |  |  |  |  |
| 73. | Publicity (MoH & OSPHCDB) |  | 10,500,000.00 | 3,500,000 |  |
| 74. | Staff Training |  | 10,000,000.00 |  |  |
| 75. | IGR Tracking |  | 1,000,000.00 |  |  |
| 76. | Renovation of block 11 at GH, Idanre |  | 16,121,587.58 |  |  |
| 77. | Health Education and Social Mobilisation |  | 2,500,000 |  |  |
| 78. | Maternal, Newborn and Child Health week |  | 15,000,000 |  |  |
| 79. | Non-communicable diseases (Guinea worm) |  |  |  |  |
| 80. | HIV/AIDS |  | 500,000 |  |  |
| 81. | Onchocerciasis |  | 250,000 |  |  |
| 82. | Tuberculosis and Leprosy Control |  | 1,000,000 |  |  |
| 83. | Midwifery service scheme/SURE-P |  | 5,000,000 |  |  |
| 84. | Reproductive Health/Family Planning |  | 500,000 |  |  |
| 85. | National programme for Immunization (ORIREWA) |  | 7,500,000 |  |  |
| 86. | Schistosomiasis |  | 250,000 |  |  |
| 87. | Nutrition |  | 1,000,000 |  |  |
| 88. | Institutional Arrangement and Coordination Mechanism |  | 27,064,000 |  |  |
| 89. | Procurement & logistics supply |  | 10,000,000 |  |  |
| 90. | Computer software acquisition |  |  |  |  |
| 91. | Basic Laboratory Equipment; and other Medical Equipment |  | 50,000,000 |  |  |
| 92. | Counterpart Fund (NHIS) |  | 0.00 |  |  |
| 93. | Printing of Free Health Cards |  | 3,000,000 |  |  |
| 94. | Purchase of office equipment |  |  |  |  |
| 95. | Health Insurance for Primary School Pupils Counterpart Contribution |  | 25,000,000 |  |  |
| 96. | Disease Surveillance and Notification |  | 250,000 |  |  |
| 97. | Renovation of existing facilities / Procurement of consumables |  | 5,000,000 |  |  |
| 98. | Payment of allowance for guest lecturers (SoM) |  | 2,000,000 |  |  |
| 99. | Upgrading of facilities for the School of Nursing and Midwifery | New | 72,000,000.00 | - | 72,000,000.00 |
| 100. | Completion of Igbotako General Hospital |  | 0.00 |  |  |
| 101. | Population Activities |  |  |  |  |
| 102. | Public Health Laboratory |  | 10,000,000 |  |  |
| 103. | Renovation of children ward, SSH Ondo |  | 9,943,753.36 |  |  |
| 104. | Health Rangers |  | 0.00 |  |  |
| 105. | School Health service |  | 2,000,000 | 750,000 | 1,250,000 |
| 106. | Updating of teachers by N&MCN |  | 0.00 |  |  |
| 107. | Procurement and equipment of the sick-bay |  | 0.00 |  |  |
| 108. | Procurement of reagents/ consumables | Ongoing | 950,000.00 | - | 950,000.00 |
| 109. | Procurement of library books School of health Tech |  | 0.00 |  |  |
| 110. | Central Blood Transfusion Services |  | 5,000,000 | 0.00 |  |
| 111. | Schistosomiasis Control |  | 0.00 |  |  |
| 112. | International Travel Control Unit (MoH& OSPHCDB) |  | 200,000 |  |  |
| 113. | Construction and Expansion of Equipment Stores and Traditional Medicine Board Offices, Oke-Eda |  | 0.00 |  |  |
| 114. | Integrated supportive supervision |  | 2,500,000 |  |  |
| 115. | FAST Network State wide scale up |  | 10,000,000 |  |  |
| 116. | Upgrading of the A&E section of Five Specialist Hospitals |  |  |  |  |
| 117. | Security and cleaning of secretariat complex |  |  |  |  |
| 118. | General services |  |  |  |  |
| 119. | Annual World Health Day |  | 3,000,000 |  |  |
| 120. | Monitoring/Quarterly Board Meetings/ Monthly Technical Review meetings |  | 5,000,000 |  |  |
| 121. | Staff capacity building (OSPHCDB) |  | 0.00 |  |  |
| 122. | District Health Management Information System |  | 1,000,000 |  |  |
| 123. | Procurement of Dental Chair for School of health Tech |  | 0.00 |  |  |
| 124. | Florence Nightingale Speech Contest | Ongoing | 1,500,000.00 |  |  |
| 125. | Provision of Sporting Facilities & NISONMG | Ongoing | 500,000.00 | - | 500,000.00 |
| 126. | Updating of Teachers by Nursing & Midwifery Council (SON) |  | 1,500,000 | - | - |

Table 10: Personnel Costs – Existing and Projected

| Number of Staff |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Items of Personnel Costs | 2015 Budget | 2015 Actual | 2016 | 2017 | 2018 | 2019 |
| Basic Salary | 7,613,404,699.17 | 2,442,033,605.49 | 8,230,090,479.80 | 8,896,727,808.67 | 9,617,362,761.17 | 7,613,404,699.17 |
| Acting Allowance | 52,501,704.76 | 36,791,954.40 | 56,754,342.85 | 61,351,444.62 | 66,320,911.63 | 52,501,704.76 |
| Professional Duty Allowance | 113,486,738.10 | 38,094,649.35 | 122,679,163.89 | 132,616,176.16 | 143,358,086.43 | 113,486,738.10 |
| Transport Allowance | 24,861,451.90 | 12,414,179.42 | 26,875,229.50 | 29,052,123.09 | 31,405,345.06 | 24,861,451.90 |
| Medical Allowance | 70,996,366.70 | 22,222,928.10 | 76,747,072.40 | 82,963,585.27 | 89,683,635.67 | 70,996,366.70 |
| Rent Supplement | 33,453,173.45 | 7,177,654.10 | 36,162,880.50 | 39,092,073.82 | 42,258,531.80 | 33,453,173.45 |
| Leave Grant | 766,218,102.85 | 195,321,975.35 | 828,281,769.18 | 895,372,592.48 | 967,897,772.48 | 766,218,102.85 |
| Domestic Staff Allowance | 494,361.00 | 205,983.75 | 534,404.24 | 577,690.98 | 624,483.95 | 494,361.00 |
| Furniture Allowance | 1,938,451.20 | 807,688.00 | 2,095,465.75 | 2,265,198.47 | 2,448,679.55 | 1,938,451.20 |
| Meal Allowance | 2,433,347.28 | 77,991.90 | 2,630,448.41 | 2,843,514.73 | 3,073,839.42 | 2,433,347.28 |
| Utility Allowance | 311,967.48 | 129,986.45 | 337,236.85 | 364,553.03 | 394,081.83 | 311,967.48 |
| Overtime Allowance | 732,500.00 | 3,527,500.00 | 791,832.50 | 855,970.93 | 925,304.58 | 732,500.00 |
| Contributory Pension | 11,125,635.44 | 3,953,231.85 | 12,026,811.91 | 13,000,983.68 | 14,054,063.35 | 11,125,635.44 |
| Other Allowance | 49,943,761.32 | 3,825,832.21 | 53,989,205.99 | 58,362,331.67 | 63,089,680.54 | 49,943,761.32 |
| Total Cost (N) | 8,741,902,260.65 | 2,766,585,160.37 | 9,449,996,343.76 | 10,215,446,047.61 | 11,042,897,177.46 | 8,741,902,260.65 |

Note: Consolidated personnel emoluments are put under the Total Cost row.

Table 11: Overhead Costs – Existing and Projected

| Items of Overheads | 2016 Approved | 2016 Actual | 2017 | 2018 | 2019 |
| --- | --- | --- | --- | --- | --- |
| Travel & Transport | 20,106,000.00 | 2,250,000.00 | 21,714,480.00 | 23,451,638.40 | 25,327,769.47 |
| Utility Services | 4,185,320.00 | 220,000.00 | 4,520,145.60 | 4,881,757.25 | 5,272,297.83 |
| Information & Communication Services | 7,500,000.00 | 0.00 | 8,100,000.00 | 8,748,000.00 | 9,447,840.00 |
| Stationery | 3,238,820.00 | 830,000.00 | 3,497,925.60 | 3,777,759.65 | 4,079,980.42 |
| Other Materials & Supplies | 9,500,000.00 | 0.00 | 10,260,000.00 | 11,080,800.00 | 11,967,264.00 |
| Printing | 2,918,020.00 | 475,000.00 | 3,151,461.60 | 3,403,578.53 | 3,675,864.81 |
| Maintenance Costs | 7,014,960.00 | 945,000.00 | 7,576,156.80 | 8,182,249.34 | 8,836,829.29 |
| Training & Staff Development | 7,961,800.00 | 790,000.00 | 8,598,744.00 | 9,286,643.52 | 10,029,575.00 |
| Operating Costs | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Staff Welfare Services | 510,880.00 | 0.00 | 551,750.40 | 595,890.43 | 643,561.67 |
| Professional Services | 1,500,000.00 | 0.00 | 1,620,000.00 | 1,749,600.00 | 1,889,568.00 |
| Grants, Contributions & Subsidy. | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Entertainment & Hospitality | 3,124,400.00 | 175,000.00 | 3,374,352.00 | 3,644,300.16 | 3,935,844.17 |
| Hotels Expenses | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Staff Loans & Advances | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Pension & Gratuity | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Advertisement & Publication | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |
| Other Overhead | 2,613,800.00 | 40,000.00 | 2,822,904.00 | 3,048,736.32 | 3,292,635.23 |
| Total Cost (N) | 70,174,000.00 | 5,725,000.00 | 75,787,920.00 | 81,850,953.60 | 88,399,029.89 |

Note: Consolidated personnel emoluments are put under the Total Cost row.

Table 12: Summary of Cancelled/Shut Down Projects

| Project Name | Justification for cancellation/shut down |
| --- | --- |

Note: If no project was cancelled in the course of scoring, leave the table blank and explain why no project was cancelled.

  - Contributions from partners

Table 13: Grants and Donor Funding

| Source / Description of Grant | Amount Expected (N) |  |  | Counterpart Funding Requirements (N) |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2016 | 2017 | 2018 | 2016 | 2017 | 2018 |
| UNICEF- immunization | 70,029,720 |  |  |  |  |  |
| UNFPA | 1,428,864 |  |  |  |  |  |
| MARIE STOPES |  |  |  |  |  |  |
| MITOSATH |  |  |  |  |  |  |
| WHO |  |  |  |  |  |  |
| BILL& MELINDA GATE | 99,500,000 |  |  |  |  |  |
| UNICEF-nutrition |  |  |  |  |  |  |
| World Bank |  |  |  |  |  |  |
| GERMAN LEPROSY FOUNDATION |  |  |  |  |  |  |
| Catholic Relief Service |  |  |  |  |  |  |
| Ford Foundation |  |  |  |  |  |  |
| Society For Family Health |  |  |  |  |  |  |
| Equitable Health Access Initiative(EHAI) | 285,979,939.35 |  |  |  |  |  |
| Institute of Human Virology of Nigeria(IHVN) |  |  |  |  |  |  |
| Hygeia Foundation |  |  |  |  |  |  |
| National Blood Transfusion Services(NBTS) |  |  |  |  |  |  |
| GAVI | 7,520,186.67 |  |  |  |  |  |

  - Program connections between Sector MDAs

This section is a description of  what elements of programmes cut across sector MDAs, including how the programmes contribute to the achievement of State and Sector broader policy objectives, and possibly how programmes in some other MDAs also contribute to the achievement  of policies which a large part of the Sector’s own programmes are intended to achieve.

  - Outline of Key Strategies

Table 14: Summary of Projects’ Expenditures and Output Measures

| Programme | Project / Activity Title |  | Amount Spent on The Project So Far (N) | Budgeted Expenditure / Cost (N) |  |  | Output | Output KPI | Base Line (i.e. Output Value in 2016) | Output Target |  |  | MTSS Activity Code | MDA Responsible |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 2017 | 2018 | 2019 |  |  |  | 2017 | 2018 | 2019 |  |  |
| Health Financing | Financial Resources |  |  | 10,000,000 | 9,000,000 | 8,100,000 | Financial needs assessment conducted Sources of fund identified Funds released | Number of financial needs assessment report available in the Ministry of Health Number of sources of fund identified Number of department/agencies with release of approved funds | 0 16 8 | 4 20 12 | 6 24 16 | 8 28 20 |  | MOH |
|  | IGR Tracking |  |  | 950,000.00 | 855,000 | 769,500 | IGR Tracking tools reviewed | Reviewed IGR Tracking tools available for the health sector | 1 | 2 | 2 | 2 |  | MOH |
|  | Counterpart Fund |  |  |  | 0 | 0 | Counterpart fund released | Number of departments/agencies with counterpart fund released | 1 | 8 | 12 | 14 |  | MOH |
|  | Health Insurance for Primary School Pupils Counterpart Contribution |  |  | 25,000,000 | 22,500,000 | 20,250,000 | Health Insurance for Primary School Pupils Counterpart Contribution released | Number of Primary School Pupils with counterpart contribution released | 0 | 1,000 | 1,500 | 1,500 |  | MOH |
| Sub-Total |  |  |  | 35,950,000 | 32,355,000 | 29,119,500 |  |  |  |  |  |  |  |  |
| Health Information Management System | Printing of Health Management Information System data tools |  |  |  | 0 | 0 | Health Management Information System data tools printed | Number of Health Management Information System data tools printed | 3 |  |  |  |  | MOH |
|  | District Health Management Information System |  |  | 1,000,000 | 900,000 | 810,000 | District Health Management Information System capacity strengthened | Number of capacity building conducted | 0 | 4 | 8 | 8 |  | MOH |
|  | Ondo State Health Statistics bulletin |  |  | 3,000,000 | 2,700,000 | 2,430,000 | Ondo State Health Statistics bulletin produced | Number of Ondo State Health Statistics bulletin produced | 0 | 4 | 4 | 4 |  | MOH |
|  | Facility based Records (Data Mop-up) |  |  | 1,200,000 | 1,080,000 | 972,000 | Facility based Records (Data Mop-up) carried out | Number of Facility based Records (Data Mop-up) carried out | 10 | 12 | 12 | 12 |  | MOH/PHCDB |
| Sub-Total |  |  |  | 5,200,000 | 4,680,000 | 4,212,000 |  |  |  |  |  |  |  |  |
| Health Research | Library (Journals) |  |  | 950,000.00 | 855,000 | 769,500 | Library (Journals) produced | Number of Library (Journals) produced | 0 | 4 | 8 | 12 |  | MOH |
|  | Monitoring and Evaluation, Research and Knowledge Management |  |  | 3,000,000 | 2,700,000 | 2,430,000 | Monitoring and Evaluation, Research and Knowledge Management carried out | Number of Monitoring and Evaluation, Research and Knowledge Management carried out | 10 | 12 | 12 | 12 |  | MOH |
| Sub-Total |  |  |  | 3,950,000 | 3,555,000 | 3,199,500 |  |  |  |  |  |  |  |  |
| Health Service Delivery | Confidential Enquiry into Maternal Death |  |  | 25,000,000 | 22,500,000 | 20,250,000 | Confidential Enquiry into Maternal Death carried out | Number of Confidential Enquiry into Maternal Death carried Number of Confidential Enquiry into Maternal Death report produced | 1 0 | 4 1 | 4 1 | 4 1 |  | MOH |
|  | Monitoring and Evaluation of Nursing Services |  |  |  | 0 | 0 | Monitoring and Evaluation of Nursing Services carried out | Number of Monitoring and Evaluation of Nursing Services carried out | 3 | 4 | 4 | 4 |  | MOH |
|  | Neonatal Intensive Nursing Training Programme |  |  | 950,000 | 855,000 | 769,500 | Neonatal Intensive Nursing Training Programme conducted | Number of Neonatal Intensive Nursing Training Programme conducted | 1 | 4 | 4 | 4 |  | MOH |
|  | Purchase of office equipment |  |  |  | 0 | 0 | Office equipment purchased | Number of Office equipment purchased | 100 | 200 | 300 | 400 |  | MOH |
|  | Payment of allowance for guest lecturers (SoM) |  |  | 4,000,000 | 3,600,000 | 3,240,000 | Allowances for guest lecturers paid | Number of allowances for guest lecturers paid | 24 | 30 | 36 | 40 |  | MOH |
|  | Care and Support of People Infected and Affected by HIV/AIDS |  |  | 514,741,451 | 463,267,306 | 416,940,575 | People Infected and Affected by HIV/AIDS received care and support | Number of People Infected and Affected by HIV/AIDS received care and support | 5,000 | 6,000 | 7,000 | 8,000 |  | ODSACA |
|  | Medical Assistance to Federal Medical Centre ,Owo |  |  |  | 0 | 0 | Medical Assistance to Federal Medical Centre, Owo received | Percentage of Medical Assistance to Federal Medical Centre ,Owo received | 0% | 50% | 60% | 70% |  | MOH |
|  | HIV Counseling and Testing |  |  | 950,000 | 855,000 | 769,500 | Mobile HIV Counseling and Testing conducted | Number of mobile HIV Counseling and Testing conducted | 50 | 60 | 80 | 90 |  | ODSACA |
|  | Condom Promotion |  |  | 6,500,000 | 5,850,000 | 5,265,000 | Condom use promoted | Number of condom use promoted | 3,000,000 | 6,000,000 | 8,000,000 | 8,000,000 |  | ODSACA |
|  | Women and men in need of HIV treatment receive treatment |  |  | 6,500,000 | 5,850,000 | 5,265,000 | Women and men in need of HIV treatment received treatment | Percentage of Women and men in need of HIV treatment that received treatment | 60% | 70% | 80% | 90% |  | ODSACA |
|  | External works at Mother and Child Hospital, Ondo (Completed but not paid) |  | 554,685,494.84 | 630,809,995.07 | 567,728,996 | 510,956,096 | External works at Mother and Child Hospital, Ondo (Completed but not paid) carried out | Percentage of External works at Mother and Child Hospital, Ondo (Completed but not paid) carried out | 50% | 60% | 70% | 90% |  | MOH |
|  | Construction of Medical Ward at Trauma and Surgical Centre Ondo | 302,127,634.87 |  | 514,741,450.57 | 463,267,306 | 416,940,575 | Construction of Medical Ward at Trauma and Surgical Centre Ondo completed | Percentage of work on construction of Medical ward at Trauma and Surgical Centre Ondo carried out | 65% | 100% |  |  |  | MOH |
|  | Upgrading of Comprehensive Health Centre, Araromi-Obu to General Hospital |  |  |  | 0 | 0 | Comprehensive Health Centre, Araromi-Obu to General Hospital upgraded | Percentage of work at c Comprehensive Health Centre, Araromi-Obu to General Hospital carried out | 15% | 60% | 100% |  |  | MOH |
|  | Construction of Science Laboratory for the Schools of Nursing and Midwifery |  | 0.00 |  | 0 | 0 | Science Laboratory for the Schools of Nursing and Midwifery constructed | Percentage of completion of Science Laboratory for the Schools of Nursing and Midwifery | 100% |  |  |  |  | MOH |
|  | Nursing and Midwifery Council of Nigeria Activities |  |  | 250,000 | 225,000 | 202,500 | Nursing and Midwifery Council of Nigeria Activities carried out | Number of Nursing and Midwifery Council of Nigeria Activities carried out | 3 | 12 | 12 | 12 |  | MOH |
|  | Communications |  |  | 2,000,000 | 1,800,000 | 1,620,000 | Communications activities carried out | Number of Communications carried out | 2 | 3 | 3 | 3 |  | MOH |
|  | Procurement of laboratory Chemicals, reagents& consumables School of health Tech |  |  | 6,750,000 | 6,075,000 | 5,467,500 | Laboratory Chemicals, reagents& consumables School of health Tech procured | Number of laboratory Chemicals, reagents& consumables School of health Tech procured |  |  |  |  |  | MOH |
|  | Additional jobs on the construction of Accident and Emergency Hospital Complex at Trauma Centre Ondo |  |  |  | 0 | 0 | Additional jobs on the construction of Accident and Emergency Hospital Complex at Trauma Centre Ondo carried out | Number of Additional jobs on the construction of Accident and Emergency Hospital Complex at Trauma Centre Ondo carried out | 0 | 4 |  |  |  | MOH |
|  | Accreditation Visit N and MC |  | 1,000,000.00 | 1,000,000.00 | 900,000 | 810,000 | Accreditation Visit N and MC carried out | Percentage of Accreditation Visit N and MC carried out | 90% |  | 100% |  |  | MOH |
|  | Procurement of anatomical models for demonstration rooms of the school |  |  | 750,000 | 675,000 | 607,500 | Anatomical models for demonstration rooms of the school procured | Number of anatomical models for demonstration rooms of the school procured | 54 | 70 | 70 | 70 |  | MOH |
|  | Management and Maintenance of Mother and Child Hospital and Other Health Facilities |  | - | 950,000 | 855,000 | 769,500 | Management and Maintenance of Mother and Child Hospital and Other Health Facilities carried out | Number of Management and Maintenance of Mother and Child Hospital and Other Health Facilities carried out | 3 | 3 | 3 | 3 |  | MOH |
|  | Maintenance of inmate of Ago-Ireti |  | 0.00 | 1,000,000 | 900,000 | 810,000 | Maintenance of inmate of Ago-Ireti carried out | Number of Maintenance of inmate of Ago-Ireti carried out | 10 | 12 | 12 | 12 |  | MOH |
|  | Assistance towards Medical Treatment |  | 0.00 | 10,000,000 | 9,000,000 | 8,100,000 | Assistance towards Medical Treatment carried out | Percentage of Medical Assistance on Treatment achieved | 95% | 100% | 100% | 100% |  | MOH |
|  | Landscaping and beautification of Laje Road Ondo (Access road to Medical Village) |  | 0.00 |  | #VALUE! | #VALUE! | Landscaping and beautification of Laje Road Ondo (Access road to Medical Village) carried out | Percentage of Landscaping and beautification of Laje Road Ondo (Access road to Medical Village) achieved | 75% | 100% |  |  |  | MOH |
|  | Construction of Surgical Ward extension and Physiotherapy Unit at Trauma Centre Ondo |  |  | 20,000,000.00 | 18,000,000 | 16,200,000 | Construction of Surgical Ward extension and Physiotherapy Unit at Trauma Centre Ondo carried out | Percentage of Construction of Surgical Ward extension and Physiotherapy Unit at Trauma Centre Ondo achieved | 80% | 100% |  |  |  | MOH |
|  | Construction of Alaanu Hostel, Medical Village Ondo |  | 0.00 | 1,000,000.00 | 900,000 | 810,000 | Construction of Alaanu Hostel, Medical Village Ondo carried out | Percentage of Construction of Alaanu Hostel, Medical Village Ondo achieved | 20% | 80% | 100% |  |  | MOH |
|  | Renovation of block 11 at GH, Idanre |  |  | 1,000,000.00 | 900,000 | 810,000 | Renovation of block 11 at GH, Idanre carried out | Percentage of Renovation of block 11 at GH, Idanre achieved | 70% | 100% |  |  |  | HMB |
|  | Health Education and Social Mobilisation |  |  | 0 | 0 | 0 | Health Education and Social Mobilisatio carried out | Number of Health Education and Social Mobilisation carried out | 50% | 100% | 100% | 100% |  | ODSACA |
|  | Maternal, Newborn and Child Health week |  | 0 | 1,000,000 | 900,000 | 810,000 | Maternal, Newborn and Child Health week carried out | Number of Maternal, Newborn and Child Health week carried out | 1 | 1 | 1 | 1 |  | ODSACA |
|  | Non-communicable diseases (Guinea worm) |  |  |  | 0 | 0 | Non-communicable diseases (Guinea worm) activities carried out | Number of Non-communicable diseases (Guinea worm) activities carried out | 0 | 1 | 1 | 1 |  | PHCDB |
|  | HIV/AIDS |  |  | 1,000,000 | 900,000 | 810,000 | HIV/AIDS activities carried out | Number of HIV/AIDS activities carried out | 4 | 4 | 4 |  |  | ODSACA/PHCDB |
|  | Onchocerciasis |  |  | 4,000,000 | 3,600,000 | 3,240,000 | Onchocerciasis activities carried out | Number of Onchocerciasis activities carried out quarterly | 4 | 4 | 4 | 4 |  | PHCDB |
|  | Midwifery service scheme/SURE-P |  |  | 2,500,000 | 2,250,000 | 2,025,000 | Midwifery service scheme/SURE-P carried out | Number of Midwifery service scheme/SURE-P carried out | 1 | 1 | 1 | 1 |  | PHCDB |
|  | National programme for Immunization (ORIREWA) |  |  | 150,000,000 | 135,000,000 | 121,500,000 | National programme for Immunization (ORIREWA) carried out | Number of National programme for Immunization (ORIREWA) carried out | 4 | 4 | 4 | 4 |  | PHCDB |
|  | Schistosomiasis |  |  | 1,000,000 | 900,000 | 810,000 | Schistosomiasis acitivities carried out | Number Schistosomiasis acitivities carried out | 4 | 4 | 4 | 4 |  | PHCDB |
|  | Institutional Arrangement and Coordination Mechanism |  |  | 10,000,000 | 9,000,000 | 8,100,000 | Institutional Arrangement and Coordination Mechanism carried out | Number of Institutional Arrangement and Coordination Mechanism carried out | 4 | 4 | 4 | 4 |  | MOH |
|  | Procurement & logistics supply |  |  | 2,000,000 | 1,800,000 | 1,620,000 | Procurement & logistics supply carried out | Number of Procurement & logistics supply carried out | 1 | 1 | 1 | 1 |  | MOH |
|  | Printing of Free Health Cards |  |  | 500,000 | 450,000 | 405,000 | Free Health Cards printed | Number of Free Health Cards printed | 1 | 1 | 1 | 1 |  | MOH |
|  | upgrading of facilities for the School of Nursing and Midwifery |  |  | 100,000,000.00 | 90,000,000 | 81,000,000 | Upgrading of facilities for the School of Nursing and Midwifery carried out | Number of facilities upgraded for the Schools of Nursing and Midwifery | 3 | 2 | 1 | 1 |  | MOH |
|  | Completion of Igbotako General Hospital |  |  |  | 0 | 0 | Completion of Igbotako General Hospital carried out | Percentage of work at Igbotako GH carried out | 50% | 50% |  |  |  | MOH |
|  | Renovation of children ward, SSHO |  |  | 280,000,000.00 | 252,000,000 | 226,800,000 | Renovation of children ward, SSHO carried out | Percentage of renovation work carried out at children ward SSH Ondo | 65% | 100% |  |  |  | HMB |
|  | School Health service |  | 11,970,000 | 20,000,000 | 18,000,000 | 16,200,000 | School health services carried out | Number of school health services carried out | 2 | 4 | 4 | 4 |  | HMB |
|  | Procurement and equipment of the sick-bay |  |  |  | 0 | 0 | Procurement and equipment of the sick-bay carried out | Number of Procurement and equipment of the sick bay carried out | 0 | 20 | 10 | 5 |  | MOH |
|  | Procurement of reagents/ consumables |  |  | 10,000,000.00 | 9,000,000 | 8,100,000 | Procurement of reagents/ consumables carried out | Number of Procurement of reagents/ consumables carried out | 30 | 30 | 30 | 30 |  | MOH |
|  | Central Blood Transfusion Services |  |  | 0 | 0 | 0 | Central Blood Transfusion Services carried out | Number of Blood Transfusion Services available Number of pints of blood dispensed to facilities Percentage increase in number of voluntary non remunerated blood donors | 4 0 0% | 4 400 10% | 4 400 20% | 4 400 30% |  | MOH |
|  | International Travel Control Unit |  |  | 1,017,688,682 | 915,919,814 | 824,327,832 | International Travel Control Unit services carried out | Number of International Travel Control Unit services carried out | 0 | 1 | 1 | 1 |  | MOH |
|  | General services |  |  |  | 0 | 0 | General services carried out | Number of General services carried out |  |  |  |  |  |  |
|  | Annual World Health Day |  |  | 1,000,000 | 900,000 | 810,000 | Annual World Health Day carried out | Number of Annual World Health Day carried out | 0 | 1 | 1 | 1 |  | MOH |
|  | Procurement of Dental Chair for School of health Tech |  |  |  | 0 | 0 | Procurement of Dental Chair for School of health Tech carried out | Number of Dental Chairs for School of health Tech procured | 1 | 1 |  |  |  | MOH |
|  | Construction of Hostels for Schools of Nursing |  | 0 | 1,000,000.00 | 900,000 | 810,000 | Construction of Hostels for Schools of Nursing carried out | Number of Hostels for School of Nursing constructed. | 2 | 1 | 1 | 1 |  | MOH |
|  | Provision of Office Furniture & Internet Services for SON |  |  | 280,000,000.00 | 252,000,000 | 226,800,000 | Provision of Office Furniture & Internet Services for SON carried out | Number of Office Furniture & Internet Services for SON provided | 0 | 5 | 5 | 5 |  | MOH |
|  | Medical Board of Enquiry and Medical Assistance |  |  | 1,017,688,682 | 915,919,814 | 824,327,832 | Medical Board of Enquiry and Medical Assistance carried out | Number of Medical Board of Enquiry and Medical Assistance carried out | 0 | 6 | 8 | 12 |  | MOH |
|  | Nigeria State Health Investment Programme DLI Re-imbursement |  |  | 327,356,517 | 294,620,865 | 265,158,779 | Nigeria State Health Investment Programme DLI Re-imbursement carried out | Number of Nigeria State Health Investment Programme DLI Re-imbursement carried out | 4 | 4 | 4 | 4 |  | MOH |
|  | Prevention of Mother to Child Transmission of HIV(PMTCT) |  |  | 2,000,000 | 1,800,000 | 1,620,000 | Prevention of Mother to Child Transmission of HIV(PMTCT) carried out | Percentage of Prevention of Mother to Child Transmission of HIV(PMTCT) carried out | 60% | 70% | 80% | 90% |  | ODSACA |
|  | Construction of hostels for School of Midwifery |  |  | 500,000 | 450,000 | 405,000 | Construction of Hostels for Schools of Midwifery carried out | Number of Hostels for School of Midwifery constructed. | 1 | 1 |  |  |  | MOH |
|  | Reproductive Health/Family Planning |  |  | 10,000,000 | 9,000,000 | 8,100,000 | Reproductive Health/Family Planning activities carried out | Number of Reproductive Health/Family Planning carried out | 2 | 6 | 6 | 6 |  | PHCDB |
|  | Public Health Laboratory |  |  | 2,500,000 | 2,250,000 | 2,025,000 | Public Health Laboratory activities carried out | Number of Public Health Laboratory activities carried out | 2 | 4 | 4 | 4 |  | MOH |
|  | Procurement of library books School of health Tech |  |  |  | 0 | 0 | Library books for School of Health Tech procured | Number of library books for School of Health Tech procured | 0 | 100 | 100 | 100 |  | MOH |
|  | Construction and Expansion of Equipment Stores and Traditional Medicine Board Offices, Oke-Eda |  |  |  | 0 | 0 | Construction and Expansion of Equipment Stores and Traditional Medicine Board Offices, Oke-Eda carried out | Number of Construction and Expansion of Equipment Stores and Traditional Medicine Board Offices, Oke-Eda carried out | 0 | 1 |  |  |  | MOH |
|  | Trauma and surgical Centre |  |  | 0 | 0 | 0 | Trauma and surgical services carried out | Number of Trauma and surgical services carried out | 0 | 1 | 1 | 1 |  | MOH |
|  | Prevention of Biomedical Transmission of HIV |  |  | 10,500,000 | 9,450,000 | 8,505,000 | Prevention of Biomedical Transmission of HIV carried out | Percentage of Prevention of Biomedical Transmission of HIV carried out | 60% | 70% | 80% | 90% |  | MOH |
|  | Festival of Surgery; Eye Camp at the MEC |  |  | 2,500,000 | 2,250,000 | 2,025,000 | Festival of Surgery; Eye Camp at the MEC carried out | Number of Festival of Surgery; Eye Camp at the MEC carried out | 0 | 3 | 3 | 3 |  | MOH |
|  | HIV/AIDS Prevention and control/rehabilitation programme for people living with HIV/AIDS |  |  |  | 0 | 0 | HIV/AIDS Prevention and control/rehabilitation programme for people living with HIV/AIDS carried out | Number of HIV/AIDS Prevention and control/rehabilitation programme for people living with HIV/AIDS carried out |  |  |  |  |  | ODSACA |
|  | Safe motherhood project-scaling up of Abiye |  |  | 0 | 0 | 0 | Safe motherhood project-scaling up of Abiye carried out | Number of Safe motherhood project-scaling up of Abiye |  |  |  |  |  | PHCDB |
|  | Basic Laboratory Equipment; and other Medical Equipment |  |  | 500,000 | 450,000 | 405,000 | Basic Laboratory Equipment; and other Medical Equipment procured | Number of Basic Laboratory Equipment; and other Medical Equipment procured | 0 | 10 | 8 | 8 |  | MOH |
|  | Renovation of existing facilities / Procurement of consumables (SoM) |  |  | 250,000 | 225,000 | 202,500 | Renovation of existing facilities / Procurement of consumables (SoM) carried out | Number of Renovation of existing facilities / Procurement of consumables (SoM) carried out | 30 | 30 | 30 | 30 |  | MOH |
|  | Emergency Preparedness and Disease Surveillance |  |  | 0 | 0 | 0 | Emergency Preparedness and Disease Surveillance carried out | Number of Emergency Preparedness and Disease Surveillance carried out | 2 | 4 | 4 | 4 |  | MOH |
|  | Nigeria State Health Investment Project Credit (World Bank Assisted) |  |  | 500,000 | 450,000 | 405,000 | Nigeria State Health Investment Project Credit (World Bank Assisted) carried out | Number of Nigeria State Health Investment Project Credit (World Bank Assisted) carried out | 4 | 4 | 4 | 4 |  | MOH |
|  | Community Medicine |  |  | 250,000 | 225,000 | 202,500 | Community Medicine activities carried out | Number of Community Medicine activities carried out | 4 | 4 | 4 | 4 |  | MOH |
|  | Free Health Drugs |  |  | 7,500,000 | 6,750,000 | 6,075,000 | Free Health Drugs procured | Percentage of Free Health Drugs procured | 25% | 75% | 80% | 90% |  | MOH |
|  | Non-communicable Diseases |  |  |  | 0 | 0 | Non-communicable Disease activities carried out | Number of Non-communicable Disease activities carried out | 1 | 4 | 4 | 4 |  | PHCDB |
|  | Nutrition |  |  | 0 | 0 | 0 | Nutrition activities carried out | Number of Nutrition activities carried out | 2 | 2 | 2 | 2 |  | PHCDB |
|  | Health Rangers |  |  |  | 0 | 0 | Health Rangers activities carried out | Number of Health Rangers activities carried out | 4 | 4 | 4 | 4 |  | PHCDB |
|  | Roll back malaria |  |  | 50,000,000.00 | 45,000,000 | 40,500,000 | Roll back Malaria activities carried out | Number of Roll back Malaria activities carried out | 20 | 25 | 30 | 30 |  | PHCDB |
|  | TBL Control Programme |  |  | 0.00 | 0 | 0 | TBL Control Programme activities carried out | Number of TBL Control Programme activities carried out | 4 | 4 | 4 | 4 |  | MOH |
| Sub-Total |  |  |  | 5,062,626,777.19 | 4,556,364,099 | 4,100,727,690 |  |  |  |  |  |  |  |  |
| Human resources | Payment of Allowance for Guest Lecturers (SoN) |  |  | 250,000.00 | 225,000 | 202,500 | Allowance to guest lecturers (SoN) paid | Number of Allowance to guest lecturers (SoN) paid |  |  |  |  |  | MOH |
|  | Human resources (capacity building) |  |  | 10,000,000 | 0 | 0 | Human resources (capacity building) activities carried out | Number of Human resources (capacity building)activities carried out. |  |  |  |  |  | MOH |
|  | Completion of Modern Laboratory |  |  | 50,000,000 | 9,000,000 | 8,100,000 | Completion of Modern Laboratory carried out | Percentage Completion of Modern Laboratory carried out |  |  |  |  |  | MOH |
|  | Procurement of Reagents/Consumables |  |  | 0.00 | 45,000,000 | 40,500,000 | Procurement of reagents/ consumables carried out | Number of Procurement of reagents/ consumables carried out |  |  |  |  |  | MOH |
|  | Provision for 1 year mandatory community experience for 50 basic students midwives for maternal & child care |  |  |  | 0 | 0 | Provision for 1 year mandatory community experience for 50 basic students midwives for maternal & child care carried out | Number of Provision for 1 year mandatory community experience for 50 basic students midwives for maternal & child care carried out |  |  |  |  |  | MOH |
|  | Population Activities |  |  |  | 0 | 0 | Population Activities carried out | Number of Population Activities carried out |  |  |  |  |  | MOH |
|  | Updating of Teachers by Nursing & Midwifery Council |  |  | 0 | 0 | 0 | Updating of Teachers by Nursing & Midwifery Council | Number of Teachers updated by Nursing & Midwifery Council |  |  |  |  |  | MOH |
|  | Florence Nightingale Speech Contest |  |  | 950,000.00 | 855,000 | 769,500 | Florence Nightingale Speech Contest carried out | Number of Florence Nightingale Speech Contest carried out |  |  |  |  |  | MOH |
|  | Staff Training |  |  | 10,000,000.00 | 9,000,000 | 8,100,000 |  |  |  |  |  |  |  |  |
| Sub-Total |  |  |  | 71,200,000.00 | 64,080,000 | 57,672,000 |  |  |  |  |  |  |  |  |
| Leadership and Governance | National Council on Health |  |  | 0 |  |  | National Council on Health activities carried out | Number of National Council on Health activities carried out |  |  |  |  |  | MOH |
|  | Updating of teachers by N&MCN |  |  |  | 0 | 0 |  |  |  |  |  |  |  |  |
|  | Integrated supportive supervision |  |  | 0 | 0 | 0 | Integrated supportive supervision carried out | Number of Integrated supportive supervision carried out |  |  |  |  |  | MOH |
|  | Accreditation exercises for School of health Tech |  |  | 72,000,000.00 | 64,800,000 | 58,320,000 | Accreditation exercises for School of health Tech carried out | Number of Accreditation exercises for School of health Tech carried out |  |  |  |  |  | MOH |
|  | Task force on Counterfeit and Fake drugs |  |  | 10,000,000 | 9,000,000 | 8,100,000 | Task force on Counterfeit and Fake drugs activities carried out | Number of task force on Counterfeit and Fake drugs carried out |  |  |  |  |  | MOH |
|  | Policy, Advocacy, Human Rights, and Legal Issues |  |  | 9,943,753 | 8,949,378 | 8,054,440 | Policy, Advocacy, Human Rights, and Legal Issues carried out | Number of Policy, Advocacy, Human Rights, and Legal Issues carried out |  |  |  |  |  | MOH |
|  | Accreditation of School of Midwifery and other activities of N&MCN |  |  | 0 | 0 | 0 | Accreditation of School of Midwifery and other activities of N&MCN carried out | Number of Accreditation of School of Midwifery and other activities of N&MCN carried out |  |  |  |  |  | MOH |
|  | Inspection of Pharmaceutical premises and patient Medicine shops |  |  | 950,000 | 855,000 | 769,500 | Inspection of Pharmaceutical premises and patient Medicine shops carried out | Number of Inspection of Pharmaceutical premises and patient Medicine shops carried out |  |  |  |  |  | MOH |
|  | Publicity |  |  | 0.00 | 0 | 0 | Publicity carried out | Number of Publicity carried out |  |  |  |  |  | MOH |
|  | Coordination meeting platforms( SACA-LACA, SACA-CSO, SACA-LM, Biannual meeting) |  |  | 2,000,000 | 1,800,000 | 1,620,000 | Coordination meeting platforms( SACA-LACA, SACA-CSO, SACA-LM, Biannual meeting) conducted | Number of Coordination meeting platforms( SACA-LACA, SACA-CSO, SACA-LM, Biannual meeting) conducted | 1 | 2 | 2 | 2 |  | PHCDB/ODSACA |
|  | Pharmacists Council of Nig. Activities |  |  | 0 | 0 | 0 | Pharmacists Council of Nig. Activities carried out | Number of Pharmacists Council of Nig. Activities carried out |  |  |  |  |  | MOH |
|  | Meetings of State/ National Council on Health |  |  | 200,000,000 | 180,000,000 | 162,000,000 | Meetings of State/ National Council on Health conducted | Number of Meetings of State/ National Council on Health conducted |  |  |  |  |  | MOH |
|  | Monitoring/Quaterly Board Meetings/ Monthly Technical Review meetings |  |  | 0 | 0 | 0 | Monitoring/Quaterly Board Meetings/ Monthly Technical Review meetings carried out. | Number of Monitoring/Quaterly Board Meetings/ Monthly Technical Review meetings carried out |  |  |  |  |  | MOH |
|  | Provision of Sporting Facilities & NISONMG |  |  | 0.00 | 0 | 0 | Provision of Sporting Facilities & NISONMG carried out | Number of Sporting Facilities & NISONMG Provided |  |  |  |  |  |  |
|  | Activities of the Medical and Dental Council of Nigeria |  |  | 10,000,000 | 9,000,000 | 8,100,000 | Activities of the Medical and Dental Council of Nigeria carried out | Number of Activities of the Medical and Dental Council of Nigeria carried out |  |  |  |  |  | MOH |
|  | Accreditation and Registration of Private Health Facilities |  |  | 0 | 0 | 0 | Accreditation and Registration of Private Health Facilities carried out | Number of Accreditation and Registration of Private Health Facilities carried out |  |  |  |  |  | MOH |
| Sub-Total |  |  |  | 105,093,753 | 94,584,378 | 85,125,940 |  |  |  |  |  |  |  |  |
| Total |  |  |  | 5,284,020,531 | 4,755,618,477 | 4,280,056,630 |  |  |  |  |  |  |  |  |

  - Justification

  - Result Framework

  - Responsibilities and Operational Plan

The Ministry of Health serves the supervisory and regulatory role to the MDAs with the agencies having their own specific functions. The Role of the Ministry of Health is listed below:

  - Health Policy/Plan formulation and legislation

  - Regulatory functions, including quality assurance (setting of standards for personnel, infrastructure and services for registration of both public and private health institutions operating in the State), monitoring and evaluation.

  - Development and implementation of strategies for Health Sector Reform, including promotion of public-private partnership in health.

  - Development of capacity for generation and utilization of evidence-based data and information for health policy, strategy and plan development/implementation (Health Management Information System).

  - Health manpower development (medical, nursing and allied training institutions) and planning including enhancement of human resource, administrative and financial management capacity of health and health-related professionals.

  - Staff Clinic and pre-employment health screening.

  - Design and implement community and school-based Information, Education and Communication (IEC) packages on the promotion of healthy lifestyles, prevention of common infectious and non-communicable diseases, and consumers’ knowledge and awareness of their right to quality care and personal obligation to better health.

  - School Health.

  - Monitor and control trends of diseases (communicable and non-communicable) at the community and State levels.

  - Institutionalize an operational system to facilitate early/timely detection, diagnosis and response to epidemics, emergencies and disasters at the State and community levels (Emergency Preparedness).

  - Design and Implement facility development program.

  - Medical and Hospital Services

  - Establish a Sustainable Drug Management System, promote Essential Drug policy and discourage use of counterfeit, spurious and substandard drugs including institutionalization of a drug quality assurance across the entire drug chain.

  - Strengthen the capacity of the Ministry to conduct health surveys and research, including development, updating and enforcement of protocol for conduct of health surveys and research by researchers.

  - Liaise with the Federal Ministry of Health and other relevant stakeholders on policy formulation and implementation.

  - Establish a forum for effective donor interaction and coordination.

  - Representation on statutory bodies such as:

    - Medical and Dental Council of Nigeria

    - Nursing and Midwifery Council of Nigeria

    - Pharmacists Council of Nigeria

- Three Year Expenditure Projections

  - Performance Monitoring and Evaluation

There are monitoring and evaluation personnel in the different MDAs of the health sector. Every month this personnel come together with the data from their facilities to submit copies to the state coordinator. Aside this there are two electronic platforms (National Health Management Information System, NHMIS and District Health Information System, DHIS) where data generated at these facilities could be viewed and analysed. NHMIS platform encompass all diseases while DHIS takes care of HIV data. Personnel were trained to handle these platform as well as the tools where the data were being generated. The analysis of these data were carried out monthly, quarterly and annually in some cases. In addition national HIV data are being collated biannually on zonal bases.

In the last quarter of every year each MDA in the health sector reviews their annual budget plan implementation and prepares another plan for the coming year which goes through the government budget defence and approval plan. During the budget implementation review, performance of the previous year as well as other emerging health issues, usually determines the area of focus in the coming year. Earlier there would have been meeting of the budget officers from the different MDAs with the Director of budget at the MEP&B for orientation on the form the following year’s budget would take and the envelope for each MDA. It is worthy of note that the State government operates e-budgeting with all the MDAs representation on the platform/portal

Some of the key assumptions made in working out the cost of the document is that the budget for the first year is 8% higher than the presumptive cost for the next year except where such item is fixed and not controlled directly by the MDA (such as registration fees etc). Another assumption is that partners will continue to work with government in those areas of competence because no cost was attached to those areas to avoid duplication of effort as well as waste of funds.

  - Public Involvement

The table below shows a projection for the Year 2017-2019 for Personnel, Overheads and Capital of the MDAs under the health sector. The year 2016 is used as the baseline for calculation with a projected inflation rate of 8%. Subsequently the inflation rate can be reviewed based on economic realities.

Table 15: Year 2017-2019 for Personnel, Overheads and Capital for health sector

| MDA | Personnel (N) in M) |  |  |  | Overhead (N) in (M) |  |  |  | Capital (N) in (B) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2016 (Millions) | 2017 | 2018 | 2019 | 2016 | 2017 | 2018 | 2019 | 2016 | 2017 | 2018 | 2019 |
| Ministry of Health | 545,050,302.31 | 588,654,326.49 | 635,746,672.61 | 686,606,406.42 | 10,400,000 | 11,232,000 | 12,130,560 | 13,101,004.8 | 4,183,500,000 | 4,518,180,000 | 4,879,634,400 | 5,270,005,152 |
| Hospitals’ Management Board | 7,584,336,962.45 | 8,191,083,919.45 | 8,846,370,633.01 | 9,554,080,283.65 | 14,880,000 | 16,070,400 | 17,355,672 | 18,744,125.76 | 56,700,000 | 61,236,000 | 66,134,880 | 71,425,670.4 |
| Primary Healthcare Board | 674,877,644.76 | 728,867,856.34 | 787,177,284.85 | 850,151,467.64 | 12,180,000 | 13,154,400 | 14,206,752 | 15,343,292.16 | 100,000,000 | 108,000,000 | 116,640,000 | 125,971,200 |
| Emergency Medical Service | 120,351,900.75 | 129,980,052.81 | 140,378,457.03 | 151,608,733.59 | 20,000,000 | 21,600,000 | 23,328,000 | 25,194,240 | 200,000,000 | 216,000,000 | 233,280,000 | 251,942,400 |
| ODSACA | 25,383,531.40 | 27,414,213.91 | 29,607,351.02 | 31,975,939.10 | 4,604,000 | 4,972,320 | 5,370,105.6 | 5,799,714.05 | 66,000,000 | 71,280,000 | 76,982,400 | 83,140,992 |
| School of Nursing | 0.00 | 0.00 | 0.00 | 0.00 | 2,364,000 | 2,553,120 | 2,757,369.60 | 2,977,959.17 | 200,000,00 | 216,000,000 | 233,280,000 | 251,942,400 |
| School of Midwifery | 0.00 | 0.00 | 0.00 | 0.00 | 3,000,000 | 3,240,000 | 3,499,200 | 3,779.136 | 32,000,000 | 34,560,000 | 37,324,800 | 40,310,784 |
| School of Health Technology | 0.00 | 0.00 | 0.00 | 0.00 | 2,700,000 | 2,916,000 | 3,149,280 | 3,401,222.4 | 125,000,000 | 135,000,000 | 145,800,000 | 157,464,000 |

Monitoring and Evaluation

  - Identifying Sources of Data against the Results Framework

Table 16: Data Sources for Outcome and Output KPIs

| Outcome KPIs | Possible Data Sources |
| --- | --- |
| 1a Percentage of LGAs with operational plans consistent with the SSHDP and priorities | LGAs Operational Plans |
| b. % of Stakeholders constituencies playing their assigned roles in the SSHDP( disaggregated by stakeholders constituencies) | SSHDP Annual review report |
| - % of LGAs implementing their peer review recommendations | LGA/SSHDP Annual Review Report |
| 2a. % of LGAs with functioning public health facility providing minimum health care package according to quality of care standards | NPHCDA Survey Report |
| 2b.% of health facilities with implementing the complete package of essential care package | NPHCDA Survey Report |
| 2c. % of the population having access to an essential care package | MICS/NDHS |
| 2d. Proportion of tuberculosis cases detected and cured under directly observed treatment short course | SMOH |
| Output KPIs | Possible Data Sources |
| 2e. % of health institutions with basic medical equipment and functional logistic system appropriate to their levels 2f. Proportion of the population utilizing essential services package | Facility Survey Report MICS |
| 3a. % of wards that have appropriate HRH complement as per service delivery norm 3b. % of LGAs actively using adaptations of National/State HRH policy and plans 3c. Increased number of trained staff based on approved staffing norms by qualification 3d. % of LGAs implementing performance based management systems | Facility survey Report HR Survey Report HR Survey HR Survey |
| 4a. % of LGAs implementing state specific safety nets. 4b. LGAs allocating health funding increased by average of 5% every year. 4c. LGAs health budgets fully aligned to support state health goals and policies 4d. % of LGA budget allocated to the health sector | SSHDP Review report Attendance register State and LGA Budgets State and LGA Budgets National Health Accounts |
| 5a. % of LGAs making routine NHMIS returns to states. Proportion of facilities given the reporting format 5b. % of health facility staff trained to use the NHMIS infrastructure 5c. % of HMIS operators at the LGA level trained in analysis of data using the operational manual 5d. % of LGA PHC Coordinator trained in data dissemination | NHMIS Report State HMIS State HMIS Training reports |
| 6a. Proportion of public health facilities having active committees that include community representatives (with meeting reports and actions recommended) 6b. % of Health development committees whose members have had training in community mobilization 6c. % of health actions jointly implemented with HDCs and other related committees | SMOH HDC Reports HDC Reports |
| 7a. % of LGAs holding annual multi-sectoral development partners meetings | SSHDP Reports |
| 8a. % of State health budget spent on health research and evaluation 8b. % of health research in LGAs available in the state health research depository 8c. % LGAs aware of state health research communication strategy | State Budget State Health Research Depository Health Research Communication Strategy |

  - Conducting Annual Sector Review

The Health sector plans to carry out yearly Performance Management Review (PMR) of the Budget in the Ministries, department and agencies. Thereafter, the Sector Planning Team of Ministry of Health will review the document and submit to management and the MTSS Steering Committee who then make necessary corrections and amendments. This process will then avail Ministry of Economic Planning & Budget (MEPB) to carry out working sessions. The MTSS document will be ratified by MEPB.

The 8 priority areas of the health system will also be reviewed periodically and ascertain progress of our projections. The 8 priority areas are listed below:

- Leadership and Governance

- Health service Delivery

- Human Resources for Health

- Financing for Health

- Health Information System

- Community participation and Ownership

- Partnership for Health

- Research for Health

With the review of the projects baselines, targets and key performance indicators, the sector will be able to attain excellence in health care service delivery in Ondo State

  - Organisational Arrangements

The responsibilities for monitoring will be done quarterly at the Planning Research and Statistics department of the Ministry of Health, PHCDB, HMB  months as this will afford close monitoring of the Budget and necessary corrections or conclusions be derived. The Health Management Information System and M & E unit of the MDAs will be involved in the collation and distribution of quarterly reports. The report will be presented to the MTSS Steering committee to review which will be headed by the Permanent Secretary, analysis of data. This will assist in the preparation of Annual Budget on the same format as well as implementation and control and eventually the annual preparation of the Health Sector Performance Report.